## Projects
Projects Key | CIP # | Title | CIP Type | Year Added | Project Classification # | NEW CIP # | Budget | Project Classification 1 | Project Classification 2 | Project Classification 3 | Project Manager Prioritization Score | Review Committee Prioritization Score | Lifetime Actual Thru FY 2016 (Unaudited) | Projected Expenditures FY 2017 | Projected Expenditures FY 2018 | Projected Expenditures FY 2019 | Projected Expenditures FY 2020 | Projected Expenditures FY 2021 | Projected Expenditures FY 2022 | Projected Expenditures FY 2023 & Beyond | 2018-2022 CIP Total | Project Total | Project Manager
10 | 262 | Southwest Water Treatment Plant, Sludge Treatment & Waste Wash water Treatment Facilities | Project | 2003 | 113 | 113001 | Water | Water | Treatment Plants & Facilities | Southwest | NA | NA | 47587 | 0 | 1793 | 0 | 0 | 0 | 0 | 0 | 1793 | 49380 | Partho Ghosh
69 | 291 | Rehabilitation of Primary Clarifiers Rectangular Tanks, Drain Lines, Electrical/Mechanical Building and Pipe Gallery | Project | 1999 | 211 | 211001 | Wastewater | Wastewater | WRRF | Primary Treatment | NA | NA | 0 | 10848 | 12097 | 20990 | 7968 | 0 | 0 | 0 | 41055 | 51903 | Phillip Kora
96 | 366 | Underground Electrical Duct Bank Repair and EB-1, EB-2, and EB-10 Primary Power Service Improvements - WRRF | Project | 1998 | 216 | 216001 | Wastewater | Wastewater | WRRF | General Purpose | NA | NA | 23037 | 2575 | 1532 | 0 | 0 | 0 | 0 | 0 | 1532 | 27144 | Eric Kramp
14 | 917 | Springwells Water Treatment Plant 1958 Filter Rehabilitation and Auxiliary Facilities | Project | 2002 | 114 | 114001 | Water | Water | Treatment Plants & Facilities | Springwells | NA | NA | 56759 | 20353 | 310 | 0 | 0 | 0 | 0 | 0 | 310 | 77422 | Eric Kramp
125 | 956 | As-needed CIP Implementation Assistance and Related Services (1) | Allowance | 2002 | 3804 | 380400 | Split | Centralized Services | Programs | Programs | NA | NA | 4770 | 1400 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 6270 | Gaylor Johnson / Dan Edwards
70 | 961 | Pump Station No. 2 Pumping Improvements | Project | 2003 | 211 | 211002 | Wastewater | Wastewater | WRRF | Primary Treatment | NA | NA | 456 | 1157 | 1304 | 616 | 0 | 0 | 0 | 0 | 1920 | 3533 | Alfredo Lava
126 | 1026 | Department-wide General Engineering Services on an As-needed Basis (1) | Allowance | 2004 | 3805 | 380500 | Split | Centralized Services | Programs | Programs | NA | NA | 10065 | 228 | 228 | 0 | 0 | 0 | 0 | 0 | 228 | 10521 | Beena Chackunkal
97 | 1028 | Plant-wide Fire Alarm Systems Upgrade/ Integration and Fire Protection Improvements | Project | 2004 | 216 | 216002 | Wastewater | Wastewater | WRRF | General Purpose | NA | NA | 5390 | 624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6014 | Vinod Sharma
127 | 1031 | General Engineering Services (1) | Allowance | 2004 | 3806 | 380600 | Split | Centralized Services | Programs | Programs | NA | NA | 14011 | 446 | 436 | 386 | 0 | 0 | 0 | 0 | 822 | 15279 | Grant Gartrell / Sanjeev Mungarwadi
52 | 1047 | Wick Road Station Rehabilitation | Project | 2004 | 132 | 132001 | Water | Water | SCC | Pump Station/Reservoir | NA | NA | 13452 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13702 | Mini Panicker
15 | 1071 | Springwells Water Treatment Plant - Low Lift and High Lift Pump Station | Project | 2004 | 114 | 114002 | Water | Water | Treatment Plants & Facilities | Springwells | 72 | 69.2 | 0 | 0 | 1500 | 2000 | 12500 | 22000 | 21500 | 26500 | 59500 | 86000 | Grant Gartrell
78 | 1100 | Returned Activated Sludge (RAS) Pumps, Influent Mixed Liquor System and Motor Control Centers (MCC) Improvements for Secondary Clarifiers | Project | 2005 | 212 | 212001 | Wastewater | Wastewater | WRRF | Secondary Treatment & Disinfection | NA | NA | 24060 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24175 | Nicolas Nicolas
34 | 1112 | Parallel 42-Inch Main in 24 Mile Road from Rochester Station to Romeo Plank Road | Project | 2005 | 122 | 122001 | Water | Water | Field Services | Transmission System | NA | NA | 26926 | 2367 | 715 | 0 | 0 | 0 | 0 | 0 | 715 | 30008 | Greg Marker
81 | 1117 | Study, Design, & Construction Management Services for Modified Detroit River Outfall No. 2 - WRRF | Project | 2006 | 212 | 212002 | Wastewater | Wastewater | WRRF | Secondary Treatment & Disinfection | NA | NA | 8449 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8482 | Alfredo Lava
98 | 1140 | Study/ Repair Potable Water, Screened Final Effluent, Natural Gas and Compressed Air Pipe Lines at the WRRF | Project | 2006 | 216 | 216003 | Wastewater | Wastewater | WRRF | General Purpose | NA | 55.6 | 0 | 50 | 690 | 1900 | 1150 | 1210 | 0 | 0 | 4950 | 5000 | Sanjeev Mungarwadi
71 | 1141 | Rehabilitation of Primary Clarifiers | Project | 2006 | 211 | 211003 | Wastewater | Wastewater | WRRF | Primary Treatment | NA | NA | 1 | 220 | 240 | 120 | 0 | 0 | 0 | 0 | 360 | 581 | Beena Chackunkal
86 | 1144 | Replacement of Belt Filter Presses for Complex I and Upper Level Complex II | Project | 2006 | 213 | 213001 | Wastewater | Wastewater | WRRF | Residuals Management | NA | NA | 29 | 1872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1901 | Vinod Sharma / Nicolas Nicolas
128 | 1147 | As-needed Engineering Services for Concrete Testing, Geotechnical Soil Borings, other Testing Services, and Related Services | Allowance | 2006 | 3807 | 380700 | Water | Water | Programs | Programs | NA | NA | 0 | 650 | 907 | 333 | 333 | 333 | 0 | 0 | 1906 | 2556 | Greg Marker
129 | 1153 | Consolidated Process Control System Upgrades | Project | 2006 | 361 | 361001 | Split | Centralized Services | Engineering | General Purpose | NA | NA | 3928 | 640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4568 | Biren Saparia
130 | 1164 | Geotechnical and Related Services on an As-Needed Basis | Allowance | 2007 | 3808 | 380800 | Split | Centralized Services | Programs | Programs | NA | NA | 2441 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2573 | Beena Chackunkal
27 | 1166 | Yard Piping, Valves and Venturi Meters Replacement at Water Works Park | Project | 2007 | 115 | 115001 | Water | Water | Treatment Plants & Facilities | Water Works Park | 58.6 | 65.4 | 0 | 0 | 5500 | 27900 | 20500 | 0 | 0 | 0 | 53900 | 53900 | Grant Gartrell
53 | 1170 | Booster Stations and Reservoirs Inspection, Rehabilitation and Inspection Repair Program | Program | 2007 | 1707 | 170700 | Water | Water | Programs | Programs | NA | NA | 9571 | 2316 | 88 | 0 | 0 | 0 | 0 | 0 | 88 | 11975 | Valerion Farr
131 | 1182 | General Engineering Services (1) | Allowance | 2007 | 3809 | 380900 | Split | Centralized Services | Programs | Programs | NA | NA | 28 | 1250 | 1154 | 0 | 0 | 0 | 0 | 0 | 1154 | 2432 | Sanjeev Mungarwadi
72 | 1189 | Pump Station 1 Rack & Grit and MPI Sampling Station 1 Improvements | Project | 2008 | 211 | 211004 | Wastewater | Wastewater | WRRF | Primary Treatment | NA | NA | 13887 | 2303 | 2652 | 2652 | 0 | 0 | 0 | 0 | 5304 | 21494 | Partho Ghosh
79 | 1194 | Aeration System Improvements | Project | 2008 | 212 | 212003 | Wastewater | Wastewater | WRRF | Secondary Treatment & Disinfection | NA | NA | 0 | 2348 | 11197 | 2658 | 0 | 0 | 0 | 0 | 13855 | 16203 | Phillip Kora
132 | 1206 | Data Center Reliability/Availability Improvements (1) | Project | 2009 | 361 | 361002 | Split | Centralized Services | Engineering | General Purpose | NA | NA | 6003 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6013 | Biren Saparia
133 | 1207 | SCADA Radio Network Upgrade (1) | Project | 2009 | 361 | 361003 | Split | Centralized Services | Engineering | General Purpose | NA | NA | 6221 | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6439 | Biren Saparia
35 | 1216 | Replacement of Five (5) PRV Pits of Treated Water Transmission System | Project | 2010 | 122 | 122002 | Water | Water | Field Services | Transmission System | NA | NA | 1015 | 1205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2220 | Eric Kramp
87 | 1221 | Rehabilitation of Central Offload Facility | Project | 2010 | 213 | 213002 | Wastewater | Wastewater | WRRF | Residuals Management | NA | 60.2 | 0 | 800 | 5850 | 6750 | 4350 | 0 | 0 | 0 | 16950 | 17750 | Beena Chackunkal
82 | 1222 | Replacement of Chlorination and Dechlorination Equipment at the WRRF | Project | 2010 | 212 | 212004 | Wastewater | Wastewater | WRRF | Secondary Treatment & Disinfection | NA | 52.8 | 0 | 0 | 400 | 2800 | 1800 | 0 | 0 | 0 | 5000 | 5000 | Sanjeev Mungarwadi
99 | 1223 | Rehabilitation of Grit and Screening System at PS-2 and Rehabilitation of Sampling Sites at WRRF | Project | 2010 | 216 | 216004 | Wastewater | Wastewater | WRRF | General Purpose | NA | 64.8 | 0 | 0 | 2500 | 2500 | 0 | 0 | 0 | 0 | 5000 | 5000 | Beena Chackunkal
54 | 1226 | Replacement of Switchgear at Joy Road Pumping Station | Project | 2010 | 132 | 132002 | Water | Water | SCC | Pump Station/Reservoir | NA | NA | 611 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612 | Jorge Nichols
1 | 1227 | Energy Management: Lake Huron Water Treatment Plant Low Lift Pumping Improvements | Project | 2010 | 111 | 111001 | Water | Water | Treatment Plants & Facilities | Lake Huron | 64.6 | 71.6 | 0 | 200 | 2500 | 3000 | 0 | 0 | 0 | 0 | 5500 | 5700 | Grant Gartrell
36 | 1230 | Water Transmission Improvement Program | Program | 2010 | 1704 | 170400 | Water | Water | Programs | Programs | NA | NA | 0 | 0 | 10000 | 10000 | 10000 | 10000 | 10000 | 0 | 50000 | 50000 | Biren Saparia
66 | 1233 | Comprehensive Water Master Plan Update | Project | 2010 | 161 | 161001 | Water | Water | General Purpose | General Purpose | NA | NA | 0 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290 | Grant Gartrell
83 | 1235 | Rouge River Outfall No. 2 (RRO-2) Segment 1 - WRRF Modifications | Project | 2011 | 212 | 212005 | Wastewater | Wastewater | WRRF | Secondary Treatment & Disinfection | NA | NA | 12125 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12187 | Partho Ghosh
100 | 1237 | Rehabilitation of the Main Plant Maintenance Building, Replacement of Various Plant Maintenance Areas and Work Environment Improvement | Project | 2011 | 216 | 216005 | Wastewater | Wastewater | WRRF | General Purpose | NA | 39 | 0 | 0 | 1500 | 6000 | 5400 | 0 | 0 | 0 | 12900 | 12900 | Beena Chackunkal
109 | 1241 | Fairview Pumping Station - Replace Four Sanitary Pumps | Project | 2011 | 232 | 232001 | Wastewater | Wastewater | SCC | Pumping Stations | NA | NA | 128 | 472 | 2100 | 14350 | 15350 | 0 | 0 | 0 | 31800 | 32400 | Jorge Nichols
88 | 1253 | Sewage Sludge Incinerator Air Quality Improvements at WRRF | Project | 2012 | 213 | 213003 | Wastewater | Wastewater | WRRF | Residuals Management | NA | NA | 33043 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36043 | Kashmira Pate
89 | 1254 | Biosolids Dryer Facility at WRRF | Project | 2012 | 213 | 213004 | Wastewater | Wastewater | WRRF | Residuals Management | NA | NA | 134191 | 1691 | 60 | 26 | 0 | 0 | 0 | 0 | 86 | 135968 | Darrel Field
67 | 1256 | Water Treatment Plant /Pump Station Allowance | Allowance | 2012 | 1701 | 170100 | Water | Water | Programs | Programs | NA | 64.4 | 0 | 12645 | 19650 | 20000 | 20000 | 10000 | 10000 | 0 | 79650 | 92295 | Grant Gartrell
117 | 1257 | Wastewater Treatment Plant, Lift Station and Wastewater Collection System Structures Allowance | Allowance | 2012 | 2601 | 260100 | Wastewater | Wastewater | Programs | Programs | NA | NA | 0 | 5587 | 12000 | 12000 | 15000 | 15000 | 12000 | 0 | 66000 | 71587 | Sanjeev Mungarwadi & Biren Saparia
103 | 1263 | Sewer and Interceptor Evaluation and Rehabilitation Program | Program | 2013 | 2602 | 260200 | Wastewater | Wastewater | Programs | Programs | NA | NA | 0 | 2612 | 8000 | 8000 | 20000 | 20000 | 20000 | 0 | 76000 | 78612 | Mini Panicker
16 | 1264 | Water Production Flow Metering Improvements at NE, SW, and SPW WTP | Project | 2014 | 114 | 114003 | Water | Water | Treatment Plants & Facilities | Springwells | 56.2 | 41.4 | 0 | 1000 | 8800 | 2100 | 1000 | 0 | 0 | 0 | 11900 | 12900 | Grant Gartrell
17 | 1265 | Miscellaneous Concrete Improvements at Springwells WTP | Project | 2014 | 114 | 114004 | Water | Water | Treatment Plants & Facilities | Springwells | NA | NA | 398 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 998 | Jorge Nichols
18 | 1266 | Administration Building Improvements at Springwells WTP | Project | 2014 | 114 | 114005 | Water | Water | Treatment Plants & Facilities | Springwells | 21.4 | 35.4 | 0 | 0 | 0 | 300 | 1700 | 0 | 0 | 0 | 2000 | 2000 | Grant Gartrell
19 | 1267 | Replacement of Rapid Mix Units at Springwells WTP 1958 Process Train | Project | 2014 | 114 | 114006 | Water | Water | Treatment Plants & Facilities | Springwells | 72 | 69.4 | 0 | 100 | 875 | 275 | 0 | 0 | 0 | 0 | 1150 | 1250 | Grant Gartrell
20 | 1268 | Powdered Activated Carbon System Improvements at Springwells WTP | Project | 2014 | 114 | 114007 | Water | Water | Treatment Plants & Facilities | Springwells | 67.6 | 43.4 | 0 | 0 | 0 | 0 | 900 | 2000 | 0 | 0 | 2900 | 2900 | Grant Gartrell
21 | 1269 | 1930 Sedimentation Basin Sluice Gates, Guides & Hoists Improvements at Springwells WTP | Project | 2014 | 114 | 114008 | Water | Water | Treatment Plants & Facilities | Springwells | 59.8 | 47.6 | 0 | 0 | 1200 | 2000 | 4000 | 300 | 0 | 0 | 7500 | 7500 | Grant Gartrell
55 | 1270 | Isolation Gate Valves for Line Pumps for West Service Center Pumping Station | Project | 2014 | 132 | 132003 | Water | Water | SCC | Pump Station/Reservoir | 76.2 | 54.4 | 0 | 0 | 521 | 1000 | 0 | 0 | 0 | 0 | 1521 | 1521 | Grant Gartrell
56 | 1271 | Hydraulic Surge Control for North Service Center Pumping Station | Project | 2014 | 132 | 132004 | Water | Water | SCC | Pump Station/Reservoir | 37.2 | 20.6 | 0 | 200 | 500 | 2000 | 100 | 0 | 0 | 0 | 2600 | 2800 | Grant Gartrell
8 | 1272 | Yard Piping Replacement at Northeast Water Treatment Plant | Project | 2014 | 112 | 112001 | Water | Water | Treatment Plants & Facilities | Northeast | 42.4 | 62.2 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 800 | 800 | Grant Gartrell
9 | 1273 | Low Lift Pumping Plant Caisson Rehabilitation at Northeast WTP | Project | 2014 | 112 | 112002 | Water | Water | Treatment Plants & Facilities | Northeast | NA | NA | 0 | 150 | 1183 | 0 | 0 | 0 | 0 | 0 | 1183 | 1333 | Grant Gartrell
28 | 1274 | Miscellaneous Concrete and Road Improvements at Waterworks Park WTP | Project | 2014 | 115 | 115002 | Water | Water | Treatment Plants & Facilities | Water Works Park | NA | NA | 761 | 2275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3036 | Jorge Nichols
11 | 1277 | High Lift Pump Discharge Valve Actuators Replacement at Southwest WTP | Project | 2014 | 113 | 113002 | Water | Water | Treatment Plants & Facilities | Southwest | 64 | 46.6 | 0 | 160 | 160 | 900 | 900 | 0 | 0 | 0 | 1960 | 2120 | Grant Gartrell
120 | 1279 | Roofing Systems Replacement at Water Plants and Booster Pump Stations | Project | 2014 | 331 | 331001 | Water | Centralized Services | Facilities | General Purpose | NA | NA | 0 | 3000 | 3000 | 3000 | 2500 | 0 | 0 | 0 | 8500 | 11500 | Grant Gartrell
2 | 1280 | Miscellaneous Mechanical Improvements at Lake Huron WTP | Project | 2014 | 111 | 111002 | Water | Water | Treatment Plants & Facilities | Lake Huron | 66.8 | 77 | 0 | 270 | 1030 | 3130 | 3050 | 422 | 0 | 0 | 7632 | 7902 | Grant Gartrell
12 | 1283 | Replacement of Butterfly Valves and Sluice Gates for Rapid Mix Chamber at Southwest WTP | Project | 2014 | 113 | 113003 | Water | Water | Treatment Plants & Facilities | Southwest | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2940 | 0 | 2940 | Grant Gartrell
90 | 1284 | Complex I Incinerators Decommissioning and Reusability at Wastewater Treatment Plant (WRRF) | Project | 2014 | 213 | 213005 | Wastewater | Wastewater | WRRF | Residuals Management | NA | 36 | 0 | 0 | 900 | 200 | 0 | 0 | 0 | 0 | 1100 | 1100 | Beena Chackunkal
94 | 1285 | Construction of new Industrial Waste Control Division and Analytical Laboratory Operations | Project | 2014 | 214 | 214001 | Wastewater | Wastewater | WRRF | IWC | NA | 51.4 | 0 | 0 | 5000 | 2000 | 0 | 0 | 0 | 0 | 7000 | 7000 | Phillip Kora
104 | 1286 | Oakwood District Intercommunity Relief Sewer Modification at Oakwood District | Project | 2014 | 222 | 222001 | Wastewater | Wastewater | Field Services | Interceptors | NA | 51.8 | 0 | 0 | 0 | 550 | 2750 | 5500 | 2200 | 0 | 11000 | 11000 | Tarlochan Bhullar
73 | 1287 | Pump Station No. 2 Improvements Phase II at Wastewater Treatment Plant (WRRF) | Project | 2014 | 211 | 211005 | Wastewater | Wastewater | WRRF | Primary Treatment | NA | 50.8 | 0 | 0 | 600 | 1700 | 4800 | 3700 | 0 | 0 | 10800 | 10800 | Beena Chackunkal
57 | 1288 | Energy Management: Evaluate Alternatives and Recommend Corrective Actions to Improve Power Factors (PF) at Various GLWA Booster Pumping Stations | Project | 2014 | 132 | 132005 | Water | Water | SCC | Pump Station/Reservoir |  | NA | 0 | 0 | 125 | 125 | 0 | 0 | 0 | 0 | 250 | 250 | Grant Gartrell
3 | 1289 | Evaluation of Flocculation Improvement Alternatives at the LHWTP | Project | 2014 | 111 | 111003 | Water | Water | Treatment Plants & Facilities | Lake Huron | 55.8 | 30.2 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | Grant Gartrell
68 | 1291 | As Needed Construction Materials, Environmental Media and Special Testing Services, Construction Inspection, and Other Technical Services | Allowance | 2014 | 1702 | 170200 | Water | Water | Programs | Programs | NA | NA | 0 | 0 | 500 | 500 | 500 | 0 | 0 | 0 | 1500 | 1500 | Grant Gartrell
30 | 1292 | Miscellaneous Improvements to Raw Water Tunnels, Shafts and Related Structures | Project | 2014 | 116 | 116001 | Water | Water | Treatment Plants & Facilities | General Purpose | NA | NA | 0 | 0 | 1000 | 1000 | 500 | 0 | 0 | 0 | 2500 | 2500 | Grant Gartrell
58 | 1293 | Pressure and Control Improvements at the Electric, Ford Road, Michigan, and West Chicago Water Booster Pumping Stations | Project | 2014 | 132 | 132006 | Water | Water | SCC | Pump Station/Reservoir | NA | NA | 0 | 0 | 200 | 2800 | 0 | 0 | 0 | 0 | 3000 | 3000 | Timothy Kuhns
59 | 1294 | Energy Management: Freeze Protection Pump Installation at Imlay Pumping Station | Project | 2014 | 132 | 132007 | Water | Water | SCC | Pump Station/Reservoir | 37.2 | 35.2 | 0 | 0 | 200 | 500 | 300 | 0 | 0 | 0 | 1000 | 1000 | Grant Gartrell
22 | 1295 | Springwells Water Treatment Plant Service Area Redundancy Study | Project | 2014 | 114 | 114009 | Water | Water | Treatment Plants & Facilities | Springwells | NA | NA | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | Timothy Kuhns
60 | 1296 | Needs Assessment Study for all Water Booster Pumping Stations | Project | 2014 | 132 | 132008 | Water | Water | SCC | Pump Station/Reservoir | 31.4 | 51.2 | 0 | 500 | 1200 | 0 | 0 | 0 | 0 | 0 | 1200 | 1700 | Grant Gartrell
13 | 1297 | Residual Handling Facility's Decant Flow Modifications at Southwest WTP | Project | 2014 | 113 | 113004 | Water | Water | Treatment Plants & Facilities | Southwest | 53.2 | 44.8 | 0 | 100 | 3100 | 2309 | 0 | 0 | 0 | 0 | 5409 | 5509 | Grant Gartrell
4 | 1298 | Electrical Tunnel Rehabilitation at Lake Huron WTP | Project | 2014 | 111 | 111004 | Water | Water | Treatment Plants & Facilities | Lake Huron | 46.8 | 31 | 0 | 0 | 1000 | 3000 | 1600 | 0 | 0 | 0 | 5600 | 5600 | Grant Gartrell
5 | 1299 | Miscellaneous Concrete Improvements at the Lake Huron WTP | Project | 2014 | 111 | 111005 | Water | Water | Treatment Plants & Facilities | Lake Huron | NA | NA | 0 | 600 | 323 | 0 | 0 | 0 | 0 | 0 | 323 | 923 | Jorge Nicolas
6 | 1300 | Replacement of Filter Instrumentation and Raw Water Flow Metering Improvements at Lake Huron WTP | Project | 2014 | 111 | 111006 | Water | Water | Treatment Plants & Facilities | Lake Huron | 64.2 | 62.2 | 0 | 100 | 600 | 12150 | 11780 | 0 | 0 | 0 | 24530 | 24630 | Grant Gartrell
29 | 1301 | Comprehensive Condition Assessment at Waterworks Park WTP | Project | 2014 | 115 | 115003 | Water | Water | Treatment Plants & Facilities | Water Works Park | 38 | 32 | 0 | 200 | 375 | 0 | 0 | 0 | 0 | 0 | 375 | 575 | Grant Gartrell
84 | 1302 | Rouge River Outfall (RRO) Disinfection (Alternative) | Project | 2014 | 212 | 212006 | Wastewater | Wastewater | WRRF | Secondary Treatment & Disinfection | NA | NA | 729 | 6530 | 15800 | 15520 | 9020 | 0 | 0 | 0 | 40340 | 47599 | Phillip Kora
65 | 1303 | Suburban Water Meter Pit Rehabilitation and Meter Replacement | Program | 2014 | 1709 | 170900 | Water | Water | Programs | Programs | 82.8 | NA | 0 | 500 | 4000 | 4000 | 4000 | 4000 | 4000 | 0 | 20000 | 20500 | Chandan Sood
39 | 1305 | New Waterworks Park to Northeast Transmission Main | Project | 2014 | 122 | 122003 | Water | Water | Field Services | Transmission System | 28.2 | 56.4 | 0 | 0 | 1500 | 5000 | 10000 | 38000 | 38000 | 37500 | 92500 | 130000 | Grant Gartrell
23 | 1306 | Yard Piping Improvements at Springwells WTP | Project | 2012 | 114 | 114010 | Water | Water | Treatment Plants & Facilities | Springwells | 50.6 | 62.2 | 0 | 0 | 0 | 2000 | 7000 | 8000 | 8000 | 0 | 25000 | 25000 | Grant Gartrell
24 | 1307 | Steam, Condensate Return, and Compressed Air Piping Improvements at Springwells WTP | Project | 2012 | 114 | 114011 | Water | Water | Treatment Plants & Facilities | Springwells | 63.8 | 58.8 | 0 | 300 | 3450 | 2500 | 0 | 0 | 0 | 0 | 5950 | 6250 | Grant Gartrell
91 | 1309 | Improvements to Sludge Feed Pumps at Dewatering Facilities | Project | 2016 | 213 | 213006 | Wastewater | Wastewater | WRRF | Residuals Management | NA | NA | 0 | 33 | 402 | 750 | 0 | 0 | 0 | 0 | 1152 | 1185 | Beena Chackunkal
92 | 1311 | Modification to Incinerator Sludge Feed Systems at Complex -II | Project | 2016 | 213 | 213007 | Wastewater | Wastewater | WRRF | Residuals Management | NA | 67.8 | 0 | 1500 | 9600 | 7822 | 0 | 0 | 0 | 0 | 17422 | 18922 | Tarlochan Bhullar
74 | 1312 | Rehabilitation of Main Lift Pumps at Pump Station No. 1 | Project | 2016 | 211 | 211006 | Wastewater | Wastewater | WRRF | Primary Treatment | NA | NA | 0 | 0 | 600 | 5350 | 5125 | 2054 | 0 | 0 | 13129 | 13129 | Beena Chackunkal
75 | 1314 | Replacement of Bar Racks at Pump Station No.2 | Project | 2016 | 211 | 211007 | Wastewater | Wastewater | WRRF | Primary Treatment | NA | 65.2 | 0 | 0 | 650 | 2900 | 3300 | 2817 | 0 | 0 | 9667 | 9667 | Beena Chackunkal
110 | 1315 | Freud & Conner Creek Pump Station Improvements | Project | 2016 | 232 | 232002 | Wastewater | Wastewater | SCC | Pumping Stations | 75.8 | 79.6 | 0 | 8040 | 5900 | 5100 | 2460 | 1000 | 0 | 0 | 14460 | 22500 | Mini Panicker
7 | 1318 | Lake Huron WTP-Raw Sludge Clarifier and Raw Sludge Pumping System Improvements | Project | 2016 | 111 | 111007 | Water | Water | Treatment Plants & Facilities | Lake Huron | 62.2 | 53.2 | 0 | 0 | 50 | 920 | 6163 | 0 | 0 | 0 | 7133 | 7133 | Grant Gartrell
25 | 1320 | Springwells Water Treatment Plant 1930 Filter Building-Roof Replacement | Project | 2016 | 114 | 114012 | Water | Water | Treatment Plants & Facilities | Springwells | 54.2 | 59.4 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | Grant Gartrell
40 | 1321 | 96-inch Main Relocation, Isolation Valves Installations, and New Parallel Main | Project | 2016 | 122 | 122004 | Water | Water | Field Services | Transmission System | 61.6 | 65.2 | 0 | 500 | 1500 | 6000 | 35900 | 31700 | 31700 | 31700 | 106800 | 139000 | Grant Gartrell
41 | 1323 | Transmission System Water Main Work - Replacement of Schoolcraft Water Main | Project | 2016 | 122 | 122005 | Water | Water | Field Services | Transmission System |  | NA | 0 | 0 | 0 | 7300 | 7250 | 0 | 0 | 0 | 14550 | 14550 | Greg Marker
42 | 1324 | Transmission System Water Main Work-Wick Road Parallel Water Main | Project | 2016 | 122 | 122006 | Water | Water | Field Services | Transmission System |  | NA | 0 | 10000 | 9350 | 0 | 0 | 0 | 0 | 0 | 9350 | 19350 | Greg Marker
61 | 1325 | Reservoir Inspection, Design and Rehabilitation at Imlay Station, Adams Station, Haggerty Station, LH-WTP, SP-WTP and SW-WTP | Program | 2016 | 1708 | 170800 | Water | Water | Programs | Programs | NA | NA | 0 | 50 | 3300 | 2550 | 2550 | 2550 | 0 | 0 | 10950 | 11000 | Grant Gartrell
43 | 1326 | Design and Construction of a new Newburgh Road 24" Main along Newburgh Road between Cherry Hill and Glenwood Avenue | Project | 2016 | 122 | 122007 | Water | Water | Field Services | Transmission System |  | NA | 0 | 0 | 1800 | 2200 | 0 | 0 | 0 | 0 | 4000 | 4000 | Greg Marker
31 | 1327 | Pennsylvania, Springwells and Northeast Raw Water Supply Tunnel Improvements based on Contract CS-1623 Inspection Results | Project | 2016 | 116 | 116002 | Water | Water | Treatment Plants & Facilities | General Purpose | 58.8 | 64.4 | 0 | 500 | 2000 | 10000 | 15000 | 4900 | 0 | 0 | 31900 | 32400 | Grant Gartrell
105 | 1329 | Detroit River Interceptor (DRI) Evaluation and Rehabilitation | Project | 2016 | 222 | 222002 | Wastewater | Wastewater | Field Services | Interceptors | 73.2 | 65.4 | 0 | 321 | 10000 | 5000 | 5000 | 0 | 0 | 0 | 20000 | 20321 | Mini Panicker
114 | 1330 | Scheduled Replacement Program of Critical Assets | Program | 2016 | 2603 | 260300 | Wastewater | Wastewater | Programs | Programs | NA | NA | 0 | 500 | 5000 | 5000 | 5000 | 5000 | 5000 | 0 | 25000 | 25500 | Biren Saparia
111 | 1331 | Northeast Pumping Station | Project | 2016 | 232 | 232003 | Wastewater | Wastewater | SCC | Pumping Stations | 65.2 | 89 | 0 | 0 | 2408 | 10920 | 13000 | 0 | 0 | 0 | 26328 | 26328 | Mini Panicker
106 | 1332 | North Interceptor East Arm (NIEA) Evaluation and Rehabilitation | Project | 2016 | 222 | 222003 | Wastewater | Wastewater | Field Services | Interceptors | 73.2 | 65.4 | 0 | 0 | 11000 | 12000 | 3000 | 0 | 0 | 0 | 26000 | 26000 | Mini Panicker
62 | 1334 | Study Phase Services for Proposed East Service Center Booster Pumping Station and Reservoir | Project | 2015 | 132 | 132009 | Water | Water | SCC | Pump Station/Reservoir | 25.6 | 55.6 | 0 | 400 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 500 | Grant Gartrell
63 | 1336 | West Service Center/Duval Rd Division Valve Upgrades | Project | 2017 | 132 | 132010 | Water | Water | SCC | Pump Station/Reservoir | 52.6 | 54 | 0 | 0 | 4200 | 7600 | 0 | 0 | 0 | 0 | 11800 | 11800 | Grant Gartrell
123 | 1343 | Energy Management: Electric Metering Improvement Program | Program | 2016 | 3810 | 381000 | Split | Centralized Services | Programs | Programs | NA | NA | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | 5000 | 6000 | Shaker Manns
115 | 1344 | Sewage Meter Design, Installation, Replacement and Rehabilitation Program | Program | 2014 | 2604 | 260400 | Wastewater | Wastewater | Programs | Programs | 82.8 | NA | 0 | 500 | 500 | 500 | 500 | 500 | 500 | 0 | 2500 | 3000 | Chandan Sood
64 | 1347 | Energy Management: West Service Center (WSC) VFD Installation | Project | 2016 | 132 | 132011 | Water | Water | SCC | Pump Station/Reservoir |  | NA | 0 | 0 | 1667 | 1667 | 0 | 0 | 0 | 0 | 3334 | 3334 | Mini Panicker
45 | 1350 | Water System Improvements in Joy Road from Southfield Road to Trinity | Project | 2014 | 122 | 122009 | Water | Water | Field Services | Transmission System | NA | NA | 8323 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8423 | Khader Hamad
46 | 1351 | Water Main Replacement within the City of Detroit - Joy Rd from Greenfield to Schaefer and Davison Ave from Lindwood to Livernois | Project | 2014 | 122 | 122010 | Water | Water | Field Services | Transmission System | NA | NA | 0 | 1370 | 1106 | 652 | 0 | 0 | 0 | 0 | 1758 | 3128 | Greg Marker
32 | 1355 | Genesee and Lapeer County Transmission System Improvements | Project | 2016 | 116 | 116003 | Water | Water | Treatment Plants & Facilities | General Purpose | 56.2 | 54.6 | 0 | 0 | 400 | 3200 | 3200 | 0 | 0 | 0 | 6800 | 6800 | Grant Gartrell
47 | 1356 | Transmission System Valve Assessment and Rehabilitation/Replacement | Program | 2017 | 1705 | 170500 | Water | Water | Programs | Programs | 69.4 | 66.8 | 0 | 0 | 2930 | 3100 | 3100 | 3100 | 3100 | 0 | 15330 | 15330 | Mini Panicker
112 | 1357 | Collection System Backwater Gates and Regulator Gates Rehabilitation | Project | 2017 | 233 | 233001 | Wastewater | Wastewater | SCC | In System Devices | 71.2 | 46.2 | 0 | 0 | 1301 | 3000 | 3000 | 2000 | 0 | 0 | 9301 | 9301 | Mini Panicker
124 | 1366 | Water Facility Lighting Renovations | Project | 2017 | 351 | 351001 | Water | Centralized Services | Energy Management | General Purpose | 60.8 | 60.8 | 0 | 0 | 933 | 933 | 933 | 0 | 0 | 0 | 2799 | 2799 | Shaker Manns
101 | 1381 | Rehabilitation of the Screened Final Effluent (SFE) Pump Station and Secondary Water System | Project | 2017 | 216 | 216006 | Wastewater | Wastewater | WRRF | General Purpose | 89.8 | 52.2 | 0 | 0 | 1700 | 2000 | 12000 | 15600 | 16279 | 2421 | 47579 | 50000 | Tarlochan Bhullar
76 | 1382 | Rehabilitation of Ferric Chloride Feed Systems | Project | 2017 | 211 | 211008 | Wastewater | Wastewater | WRRF | Primary Treatment | 80.2 | 57 | 0 | 0 | 400 | 1400 | 5200 | 2000 | 633 | 0 | 9633 | 9633 | Beena Chackunkal
93 | 1383 | Rehabilitation of the Ash Handling Systems | Project | 2017 | 213 | 213008 | Wastewater | Wastewater | WRRF | Residuals Management | 82.4 | 53.8 | 0 | 0 | 530 | 1045 | 6225 | 5725 | 4791 | 0 | 18316 | 18316 | Tarlochan Bhullar
95 | 1384 | Rehabilitation of Combined Sewer Overflow (CSO) Retention Treatment Basins (RTB) Screening (Replaces CIP1313) | Project | 2017 | 215 | 215001 | Wastewater | Wastewater | WRRF | CSO RTB & SDF | 82 | 90.6 | 0 | 3520 | 2247 | 6400 | 9000 | 7200 | 3610 | 0 | 28457 | 31977 | Tarlochan Bhullar
80 | 1385 | Rehabilitation of the Secondary Clarifiers | Project | 2017 | 212 | 212007 | Wastewater | Wastewater | WRRF | Secondary Treatment & Disinfection | 62.4 | 40.8 | 0 | 0 | 301 | 3576 | 5543 | 5540 | 5540 | 10499 | 20500 | 30999 | Beena Chackunkal
77 | 1386 | Rehabilitation of the Circular Primary Clarifier Scum Removal System | Project | 2017 | 211 | 211009 | Wastewater | Wastewater | WRRF | Primary Treatment | 69.8 | 49.4 | 0 | 0 | 266 | 324 | 1870 | 2671 | 2670 | 2679 | 7801 | 10480 | Tarlochan Bhullar
121 | 1387 | Roofing Systems Replacement at GLWA Wastewater Treatment Plant CSO Retention Treatment Basins (RTB) and Screening Disinfection Facilities (SDF) | Project | 2017 | 331 | 331002 | Wastewater | Centralized Services | Facilities | General Purpose | 73.4 | 40.4 | 0 | 0 | 2200 | 2060 | 1060 | 1050 | 540 | 2140 | 6910 | 9050 | Tarlochan Bhullar / Paula Anderson
118 | 1388 | Wastewater System Wide Instrumentation & Control Software and Hardware Upgrade | Project | 2017 | 251 | 251002 | Wastewater | Wastewater | General Purpose | General Purpose | 77 | 33 | 0 | 0 | 0 | 0 | 0 | 3125 | 2737 | 0 | 5862 | 5862 | Beena Chackunkal
26 | 1389 | Springwells Reservoir Fill Line Improvements | Project | 2016 | 114 | 114013 | Water | Water | Treatment Plants & Facilities | Springwells | 68.2 | NA | 0 | 200 | 3300 | 4000 | 0 | 0 | 0 | 0 | 7300 | 7500 | Grant Gartrell
113 | 1391 | Collection System In System Storage Devices (ISDs) Improvement | Project | 2017 | 233 | 233002 | Wastewater | Wastewater | SCC | In System Devices | 58.6 | 30.6 | 0 | 0 | 86 | 464 | 2000 | 1000 | 0 | 0 | 3550 | 3550 | Mini Panicker
107 | 1392 | Collection System Valve Remote Operation Structures Improvements | Project | 2017 | 222 | 222004 | Wastewater | Wastewater | Field Services | Interceptors | 72.6 | 68.2 | 0 | 0 | 341 | 1000 | 1422 | 0 | 0 | 0 | 2763 | 2763 | Mini Panicker
108 | 1393 | Collection System Access Hatch Improvements | Project | 2017 | 222 | 222005 | Wastewater | Wastewater | Field Services | Interceptors | 65.8 | 52.8 | 0 | 0 | 3196 | 2000 | 2001 | 0 | 0 | 0 | 7197 | 7197 | Mini Panicker
85 | 1399 | Phosphorous Recovery at WRRF | Project | 2017 | 213 | 213009 | Wastewater | Wastewater | WRRF | Residuals Management | 58.2 | 39.4 | 0 | 0 | 0 | 500 | 2000 | 6250 | 6250 | 0 | 15000 | 15000 | Tarlochan Bhullar
48 | 1400 | Water Transmission Main Asset Assessment Program | Program | 2017 | 1706 | 170600 | Water | Water | Programs | Programs | NA | NA | 0 | 0 | 2626 | 2000 | 2000 | 2000 | 2000 | 0 | 10626 | 10626 | Mini Panicker
33 | 1401 | Water Treatment Plant Automation Program | Program | 2017 | 1703 | 170300 | Water | Water | Programs | Programs | NA | NA | 0 | 0 | 1500 | 1500 | 1500 | 1500 | 1500 | 0 | 7500 | 7500 | Jeffrey Dorsey
102 | 1402 | DTE Primary Electric 3rd Feed Supply to WRRF | Project | 2017 | 216 | 216007 | Wastewater | Wastewater | WRRF | General Purpose | 88 | 73.4 | 0 | 0 | 3500 | 3500 | 0 | 0 | 0 | 0 | 7000 | 7000 | Tarlochan Bhullar
49 | 1403 | Park-Merriman Water Main-Final Phase | Project | 2015 | 122 | 122011 | Water | Water | Field Services | Transmission System | NA | NA | 0 | 0 | 1800 | 2200 | 0 | 0 | 0 | 0 | 4000 | 4000 | Greg Marker
50 | 1404 | 36-inch Water Main in Telegraph Road | Project | 2012 | 122 | 122012 | Water | Water | Field Services | Transmission System | NA | NA | 0 | 2000 | 5061 | 0 | 0 | 0 | 0 | 0 | 5061 | 7061 | Greg Marker
51 | 1405 | Lyon Township Transmission Main Extension Project | Project | 2017 | 122 | 122013 | Water | Water | Field Services | Transmission System | 39.4 | NA | 0 | 1300 | 10500 | 12000 | 6000 | 0 | 0 | 0 | 28500 | 29800 | Tim Kuhns
137 | 1407 | Springwells WTP Underground Fire Protection Loop Improvements | Project | 2017 | 114 | 114014 | Water | Water | Treatment Plants & Facilities | Springwells | 46.8 | NA | 0 | 0 | 380 | 2909 | 0 | 0 | 0 | 0 | 3289 | 3289
138 | 1409 | CSO Outfall Rehabilitation | Project | 2017 | 222 | 222006 | Wastewater | Wastewater | Field Services | Interceptors | 69.8 | NA | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 30000 | 36000 | Mini Panicker
139 | 1410 | Water Works Park WTP Chlorine System Upgrade | Project | 2017 | 115 | 115004 | Water | Water | Treatment Plants & Facilities | Water Works Park | 85.8 | NA | 0 | 290 | 700 | 8700 | 0 | 0 | 0 | 0 | 9400 | 9690
140 | 1411 | NIEA Evaluation and Rehabilitation from WRRF to Gratiot Ave. and Sylvester St. | Project | 2017 | 222 | 222007 | Wastewater | Wastewater | Field Services | Interceptors | 69.8 | NA | 0 | 0 | 7000 | 7000 | 7000 | 0 | 0 | 0 | 21000 | 21000 | Mini Panicker
141 | 1412 | Emergency Grating Replacement at Springwells WTP | Project | 2017 | 114 | 114015 | Water | Water | Treatment Plants & Facilities | Springwells | 100 | NA | 0 | 500 | 2000 | 0 | 0 | 0 | 0 | 0 | 2000 | 2500
37 | 1230b | 48-Inch Water Main Installation at Vining and Wick Roads in Romulus | Project | 2015 | 122 | 122014 | Water | Water | Field Services | Transmission System | NA | NA | 1021 | 3514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4535 | Greg Marker
38 | 1230c | 30-Inch Water main | Project | 2017 | 122 | 122015 | Water | Water | Field Services | Transmission System | NA | NA | 0 | 2327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2327 | Greg Marker
Total | 134 | [11 empty] | 469416 | 139470 | 298401 | 391582 | 387053 | 256747 | 219550 | 122379 | 1553333 | 2284598

## Phases
Phases Key | CIP # | Title | Project Classification # | NEW CIP # | Budget | Project Classification 1 | Project Classification 2 | Project Classification 3 | Category | Contract No | Status | Start Date | End Date | Lifetime Actual Thru FY 2016 (Unaudited) | Projected Expenditures FY 2017 | Projected Expenditures FY 2018 | Projected Expenditures FY 2019 | Projected Expenditures FY 2020 | Projected Expenditures FY 2021 | Projected Expenditures FY 2022 | Projected Expenditures FY 2023 & Beyond | 2018-2022 CIP Total | Project Total | Useful Life | TFG Financing Source Work | Cost Allocation
12 | 262 | Southwest Water Treatment Plant, Sludge Treatment & Waste Wash water Treatment Facilities | 113 | 113001 | Water | Water | Treatment Plants & Facilities | Southwest | C | SW-548 | Pending Close-out | 2010-05-12 | 2016-07-03 | 47587.1618 | 0 | 1793 | 0 | 0 | 0 | 0 | 0 | 1793 | 49380.1618 | > 20 | DE | CTA
93 | 291 | Rehabilitation of Primary Clarifiers Rectangular Tanks, Drain Lines, Electrical/Mechanical Building and Pipe Gallery | 211 | 211001 | Wastewater | Wastewater | WRRF | Primary Treatment | C | PC-757 | Active | TBD | TBD | 0 | 10848 | 12097 | 20990 | 7968 | 0 | 0 | 0 | 41055 | 51903 | > 20 | SRF | CTA
133 | 366 | Underground Electrical Duct Bank Repair and EB-1, EB-2, and EB-10 Primary Power Service Improvements - WRRF | 216 | 216001 | Wastewater | Wastewater | WRRF | General Purpose | C | PC-783 | Pending Close-out | 2012-05-21 | 2016-05-21 | 23036.5089 | 2500 | 1532 | 0 | 0 | 0 | 0 | 0 | 1532 | 27068.5089 | > 20 | Bond | CTA
134 | 366 | Underground Electrical Duct Bank Repair and EB-1, EB-2, and EB-10 Primary Power Service Improvements - WRRF | 216 | 216001 | Wastewater | Wastewater | WRRF | General Purpose | S/D/CA | CS-1449 | Pending Close-out | 2008-06-12 | 2016-06-11 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | > 20 | Bond | CTA
17 | 917 | Springwells Water Treatment Plant 1958 Filter Rehabilitation and Auxiliary Facilities | 114 | 114001 | Water | Water | Treatment Plants & Facilities | Springwells | C | SP-563 | Active | 2013-07-08 | 2018-03-14 | 56758.6188 | 20000 | 215 | 0 | 0 | 0 | 0 | 0 | 215 | 76973.6188 | > 20 | Bond | CTA
18 | 917 | Springwells Water Treatment Plant 1958 Filter Rehabilitation and Auxiliary Facilities | 114 | 114001 | Water | Water | Treatment Plants & Facilities | Springwells | S/D/CA | CS-1425 | Active | 2008-01-18 | 2018-01-18 | 0 | 353 | 95 | 0 | 0 | 0 | 0 | 0 | 95 | 448 | > 20 | Bond | CTA
192 | 956 | As-needed CIP Implementation Assistance and Related Services (1) | 3804 | 380400 | Wastewater | Centralized Services | Programs | Programs | S/D/CM | CS-1433 | Active | 2006-03-24 | 2017-07-24 | 4770.3465 | 1400 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 6270.3465 | > 20 | I&E | CTA
95 | 961 | Pump Station No. 2 Pumping Improvements | 211 | 211002 | Wastewater | Wastewater | WRRF | Primary Treatment | C | PC-795 | Active | 2016-10-17 | 2019-06-20 | 0 | 1027 | 1232 | 616 | 0 | 0 | 0 | 0 | 1848 | 2875 | > 20 | SRF | CTA
94 | 961 | Pump Station No. 2 Pumping Improvements | 211 | 211002 | Wastewater | Wastewater | WRRF | Primary Treatment | S/D/CA | CS-1444 | Active | 2010-08-11 | 2017-09-11 | 455.936 | 130 | 72 | 0 | 0 | 0 | 0 | 0 | 72 | 657.936 | > 20 | I&E | CTA
83 | 1026 | Department-wide General Engineering Services on an As-needed Basis (1) | 3805 | 380500 | Water | Centralized Services | Programs | Programs | D | CS-1499 | Active | 2010-05-12 | 2018-06-02 | 5032.3641 | 114 | 114 | 0 | 0 | 0 | 0 | 0 | 114 | 5260.3641 | > 20 | I&E | CTA
193 | 1026 | Department-wide General Engineering Services on an As-needed Basis (1) | 3805 | 380500 | Wastewater | Centralized Services | Programs | Programs | D | CS-1499 | Active | 2010-05-12 | 2018-06-02 | 5032.3641 | 114 | 114 | 0 | 0 | 0 | 0 | 0 | 114 | 5260.3641 | > 20 | I&E | CTA
136 | 1028 | Plant-wide Fire Alarm Systems Upgrade/ Integration and Fire Protection Improvements | 216 | 216002 | Wastewater | Wastewater | WRRF | General Purpose | S/D/CA | CS-1443 | Pending Close-out | 2008-06-12 | 2015-12-31 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | > 20 | Bond | CTA
135 | 1028 | Plant-wide Fire Alarm Systems Upgrade/ Integration and Fire Protection Improvements | 216 | 216002 | Wastewater | Wastewater | WRRF | General Purpose | C | PC-782 | Pending Close-out | 2013-04-15 | 2016-11-04 | 5389.939 | 601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5990.939 | > 20 | Bond | CTA
84 | 1031 | General Engineering Services (1) | 3806 | 380600 | Water | Centralized Services | Programs | Programs | D | CS-1432A | Active | 2008-01-23 | 2018-12-12 | 7005.5963 | 336 | 336 | 336 | 0 | 0 | 0 | 0 | 672 | 8013.5963 | > 20 | I&E | CTA
194 | 1031 | General Engineering Services (1) | 3806 | 380600 | Wastewater | Centralized Services | Programs | Programs | D | CS-1432A | Active | 2008-01-23 | 2018-12-12 | 7005.5963 | 110 | 100 | 50 | 0 | 0 | 0 | 0 | 150 | 7265.5963 | > 20 | I&E | CTA
59 | 1047 | Wick Road Station Rehabilitation | 132 | 132001 | Water | Water | SCC | Pump Station/Reservoir | DB | DWS-858 | Pending Close-out | 2008-11-25 | 2016-06-30 | 13451.9512 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13701.9512 | > 20 | Bond | CTA
206 | 1071 | Springwells Water Treatment Plant - Low Lift and High Lift Pump Station | 114 | 114002 | Water | Water | Treatment Plants & Facilities | Springwells | S/D/CA | CS-103 | Under Procurement | NA | NA | 0 | 0 | 1500 | 2000 | 2500 | 2000 | 1500 | 1500 | 9500 | 11000 | > 20 | DE | CTA
19 | 1071 | Springwells Water Treatment Plant - Low Lift and High Lift Pump Station | 114 | 114002 | Water | Water | Treatment Plants & Facilities | Springwells | C | NA | Not Yet Started | NA | NA | 0 | 0 | 0 | 0 | 10000 | 20000 | 20000 | 25000 | 50000 | 75000 | > 20 | DE | CTA
107 | 1100 | Returned Activated Sludge (RAS) Pumps, Influent Mixed Liquor System and Motor Control Centers (MCC) Improvements for Secondary Clarifiers | 212 | 212001 | Wastewater | Wastewater | WRRF | Secondary Treatment & Disinfection | C | PC-776 | Pending Close-out | 2010-08-23 | 2016-05-09 | 24059.704 | 115 | 0 | 0 | 0 | 0 |  | 0 | 0 | 24174.704 | > 20 | Bond | CTA
41 | 1112 | Parallel 42-Inch Main in 24 Mile Road from Rochester Station to Romeo Plank Road | 122 | 122001 | Water | Water | Field Services | Transmission System | C | WS-681 | Pending Close-out | 2014-04-07 | 2016-10-09 | 26925.667 | 2367 | 715 | 0 | 0 | 0 | 0 | 0 | 715 | 30007.667 | < 20 | Bond | CTA
112 | 1117 | Study, Design, & Construction Management Services for Modified Detroit River Outfall No. 2 - WRRF | 212 | 212002 | Wastewater | Wastewater | WRRF | Secondary Treatment & Disinfection | S/D/CA | CS-1448 | Pending Close-out | 2006-10-31 | 2016-10-31 | 8448.5937 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8481.5937 | > 20 | Bond | CTA
137 | 1140 | Study/ Repair Potable Water, Screened Final Effluent, Natural Gas and Compressed Air Pipe Lines at the WRRF | 216 | 216003 | Wastewater | Wastewater | WRRF | General Purpose | C | NA | Not Yet Started | NA | NA | 0 | 0 | 500 | 1500 | 1000 | 1110 | 0 | 0 | 4110 | 4110 | > 20 | DE | CTA
138 | 1140 | Study/ Repair Potable Water, Screened Final Effluent, Natural Gas and Compressed Air Pipe Lines at the WRRF | 216 | 216003 | Wastewater | Wastewater | WRRF | General Purpose | S/D/CA | NA | Not Yet Started | NA | NA | 0 | 50 | 190 | 400 | 150 | 100 | 0 | 0 | 840 | 890 | > 20 | DE | CTA
96 | 1141 | Rehabilitation of Primary Clarifiers | 211 | 211003 | Wastewater | Wastewater | WRRF | Primary Treatment | S/D/CA | CS-1484 | Active | 2010-08-11 | 2019-07-09 | 1.066 | 220 | 240 | 120 | 0 | 0 | 0 | 0 | 360 | 581.066 | > 20 | DE | CTA
118 | 1144 | Replacement of Belt Filter Presses for Complex I and Upper Level Complex II | 213 | 213001 | Wastewater | Wastewater | WRRF | Residuals Management | C | PC-787 | Active | 2012-05-21 | 2016-08-03 | 27.3009 | 1776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1803.3009 | > 20 | Bond | CTA
119 | 1144 | Replacement of Belt Filter Presses for Complex I and Upper Level Complex II | 213 | 213001 | Wastewater | Wastewater | WRRF | Residuals Management | S/D/CA | CS-1483 | Active | 2010-01-11 | 2016-12-31 | 1.988 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97.988 | > 20 | Bond | CTA
85 | 1147 | As-needed Engineering Services for Concrete Testing, Geotechnical Soil Borings, other Testing Services, and Related Services | 3807 | 380700 | Water | Water | Programs | Programs | D/C | CS-1488 | Active | 2009-04-08 | 2021-04-08 | 0 | 650 | 907 | 333.33 | 333 | 333 | 0 | 0 | 1906.33 | 2556.33 | > 20 | I&E | CTA
196 | 1153 | Consolidated Process Control System Upgrades | 361 | 361001 | Wastewater | Centralized Services | Engineering | General Purpose | DB | PC-773D | Pending Close-out | 2013-05-25 | 2016-05-22 | 2.9727 | 328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330.9727 | > 20 | DE | CTA
86 | 1153 | Consolidated Process Control System Upgrades | 361 | 361001 | Water | Centralized Services | Engineering | General Purpose | DB | PC-773C | Pending Close-out | 2013-05-25 | 2016-05-25 | 3925.1535 | 312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4237.1535 | < 20 | DE | CTA
87 | 1164 | Geotechnical and Related Services on an As-Needed Basis | 3808 | 380800 | Water | Centralized Services | Programs | Programs | D | CS-1490 | Pending Close-out | 2010-01-14 | 2016-07-14 | 2441.2502 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2573.2502 | > 20 | I&E | CTA
33 | 1166 | Yard Piping, Valves and Venturi Meters Replacement at Water Works Park | 115 | 115001 | Water | Water | Treatment Plants & Facilities | Water Works Park | S/D/C | NA | Not Yet Started | NA | NA | 0 | 0 | 5500 | 27900 | 20500 | 0 | 0 | 0 | 53900 | 53900 | > 20 | DE | CTA
60 | 1170 | Booster Stations and Reservoirs Inspection, Rehabilitation and Inspection Repair Program | 1707 | 170700 | Water | Water | Programs | Programs | PM | DWS-874 | Pending Close-out | 2013-07-03 | 2019-10-30 | 9570.8839 | 2316 | 88 | 0 | 0 | 0 | 0 | 0 | 88 | 11974.8839 | > 20 | DE | CTA
88 | 1182 | General Engineering Services (1) | 3809 | 380900 | Water | Centralized Services | Programs | Programs | D | CS-1481 | Active | 2008-03-27 | 2018-03-27 | 0 | 741 | 772 | 0 | 0 | 0 | 0 | 0 | 772 | 1513 | > 20 | I&E | CTA
198 | 1182 | General Engineering Services (1) | 3809 | 380900 | Wastewater | Centralized Services | Programs | Programs | D | CS-1481 | Active | 2008-03-27 | 2018-03-27 | 28.0549 | 509 | 382 | 0 | 0 | 0 | 0 | 0 | 382 | 919.0549 | > 20 | I&E | CTA
97 | 1189 | Pump Station 1 Rack & Grit and MPI Sampling Station 1 Improvements | 211 | 211004 | Wastewater | Wastewater | WRRF | Primary Treatment | C | PC-789 | Active | 2013-11-18 | 2017-07-30 | 13886.8159 | 2303 | 2652 | 2652 | 0 | 0 | 0 | 0 | 5304 | 21493.8159 | > 20 | DE | CTA
108 | 1194 | Aeration System Improvements | 212 | 212003 | Wastewater | Wastewater | WRRF | Secondary Treatment & Disinfection | C | PC-796 | Under Procurement | TBD | TBD | 0 | 2242 | 11100 | 2642 | 0 | 0 | 0 | 0 | 13742 | 15984 | > 20 | SRF | CTA
109 | 1194 | Aeration System Improvements | 212 | 212003 | Wastewater | Wastewater | WRRF | Secondary Treatment & Disinfection | S/D/CA | CS-1498 | Active | 2012-02-21 | 2018-02-28 | 0 | 106 | 97 | 16 | 0 | 0 | 0 | 0 | 113 | 219 | > 20 | SRF | CTA
89 | 1206 | Data Center Reliability/Availability Improvements (1) | 361 | 361002 | Water | Centralized Services | Engineering | General Purpose | DB | DWS-881 | Pending Close-out | 2013-01-29 | 2016-02-27 | 2845.759 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2850.759 | < 20 | DE | CTA
199 | 1206 | Data Center Reliability/Availability Improvements (1) | 361 | 361002 | Wastewater | Centralized Services | Engineering | General Purpose | DB | DWS-881 | Pending Close-out | 2013-01-29 | 2016-02-27 | 3157.5981 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3162.5981 | < 20 | DE | CTA
90 | 1207 | SCADA Radio Network Upgrade (1) | 361 | 361003 | Water | Centralized Services | Engineering | General Purpose | DB | DWS-882 | Pending Close-out | 2013-03-26 | 2016-09-30 | 3374.9141 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3483.9141 | < 20 | DE | CTA
200 | 1207 | SCADA Radio Network Upgrade (1) | 361 | 361003 | Wastewater | Centralized Services | Engineering | General Purpose | DB | DWS-882 | Pending Close-out | 2013-03-26 | 2016-09-30 | 2845.759 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2954.759 | > 20 | DE | CTA
42 | 1216 | Replacement of Five (5) PRV Pits of Treated Water Transmission System | 122 | 122002 | Water | Water | Field Services | Transmission System | C | DWS-891 | Active | 2015-05-14 | 2017-06-30 | 1014.6368 | 1205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2219.6368 | > 20 | DE | CTA
120 | 1221 | Rehabilitation of Central Offload Facility | 213 | 213002 | Wastewater | Wastewater | WRRF | Residuals Management | C | NA | Not Yet Started | NA | NA | 0 | 0 | 5500 | 6500 | 4000 | 0 | 0 | 0 | 16000 | 16000 | > 20 | SRF | CTA
121 | 1221 | Rehabilitation of Central Offload Facility | 213 | 213002 | Wastewater | Wastewater | WRRF | Residuals Management | S/D/CA | CS-1701 | Under Procurement | NA | NA | 0 | 800 | 350 | 250 | 350 | 0 | 0 | 0 | 950 | 1750 | > 20 | DE | CTA
113 | 1222 | Replacement of Chlorination and Dechlorination Equipment at the WRRF | 212 | 212004 | Wastewater | Wastewater | WRRF | Secondary Treatment & Disinfection | C | NA | Not Yet Started | NA | NA | 0 | 0 | 400 | 2800 | 1800 | 0 | 0 | 0 | 5000 | 5000 | > 20 | DE | CTA
139 | 1223 | Rehabilitation of Grit and Screening System at PS-2 and Rehabilitation of Sampling Sites at WRRF | 216 | 216004 | Wastewater | Wastewater | WRRF | General Purpose | C | NA | Not Yet Started | NA | NA | 0 | 0 | 2500 | 2500 | 0 | 0 | 0 | 0 | 5000 | 5000 | > 20 | DE | CTA
61 | 1226 | Replacement of Switchgear at Joy Road Pumping Station | 132 | 132002 | Water | Water | SCC | Pump Station/Reservoir | C | DWS-896 | Pending Close-out | 2015-03-13 | 2016-03-07 | 611.287 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612.287 | > 20 | Bond | CTA
1 | 1227 | Energy Management: Lake Huron Water Treatment Plant Low Lift Pumping Improvements | 111 | 111001 | Water | Water | Treatment Plants & Facilities | Lake Huron | D/C | NA | Not Yet Started | NA | NA | 0 | 200 | 2500 | 3000 | 0 | 0 | 0 | 0 | 5500 | 5700 | > 20 | DE | CTA
43 | 1230 | Water Transmission Improvement Program | 1704 | 170400 | Water | Water | Programs | Programs | C | NA | Not Yet Started | NA | NA | 0 | 0 | 9000 | 9000 | 9000 | 9000 | 9000 | 0 | 45000 | 45000 | > 20 | DE | CTA
245 | 1230 | Water Transmission Improvement Program | 1704 | 170400 | Water | Water | Programs | Programs | D | NA | Not Yet Started | NA | NA | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | 5000 | 5000 | < 20 | DE | CTA
74 | 1233 | Comprehensive Water Master Plan Update | 161 | 161001 | Water | Water | General Purpose | General Purpose | S | CS-1528 | Active | 2013-06-03 | 2016-12-31 | 0 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290 | > 20 | SWIPP Grant/ Bond | CTA
114 | 1235 | Rouge River Outfall No. 2 (RRO-2) Segment 1 - WRRF Modifications | 212 | 212005 | Wastewater | Wastewater | WRRF | Secondary Treatment & Disinfection | C | PC-786 | Pending Close-out | 2012-05-21 | 2016-12-21 | 12124.766 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12186.766 | > 20 | SRF | CTA
141 | 1237 | Rehabilitation of the Main Plant Maintenance Building, Replacement of Various Plant Maintenance Areas and Work Environment Improvement | 216 | 216005 | Wastewater | Wastewater | WRRF | General Purpose | S/D/CA | NA | Not Yet Started | NA | NA | 0 | 0 | 1000 | 440 | 400 | 0 | 0 | 0 | 1840 | 1840 | > 20 | DE | CTA
140 | 1237 | Rehabilitation of the Main Plant Maintenance Building, Replacement of Various Plant Maintenance Areas and Work Environment Improvement | 216 | 216005 | Wastewater | Wastewater | WRRF | General Purpose | C | NA | Not Yet Started | NA | NA | 0 | 0 | 500 | 5560 | 5000 | 0 | 0 | 0 | 11060 | 11060 | > 20 | DE | CTA
165 | 1241 | Fairview Pumping Station - Replace Four Sanitary Pumps | 232 | 232001 | Wastewater | Wastewater | SCC | Pumping Stations | D/CA | CS-1747 | Not Yet Started | 2016-07-05 | 2021-10-05 | 128.0939 | 471.9061 | 1400 | 350 | 350 | 0 | 0 | 0 | 2100 | 2700 | > 20 | Bond | CTA
164 | 1241 | Fairview Pumping Station - Replace Four Sanitary Pumps | 232 | 232001 | Wastewater | Wastewater | SCC | Pumping Stations | C | NA | Not Yet Started | NA | NA | 0 | 0 | 700 | 14000 | 15000 | 0 | 0 | 0 | 29700 | 29700 | > 20 | Bond | CTA
122 | 1253 | Sewage Sludge Incinerator Air Quality Improvements at WRRF | 213 | 213003 | Wastewater | Wastewater | WRRF | Residuals Management | DB | PC-791 | Not Yet Started | 2012-12-17 | 2017-06-30 | 33042.857 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36042.857 | > 20 | SRF | CTA
123 | 1254 | Biosolids Dryer Facility at WRRF | 213 | 213004 | Wastewater | Wastewater | WRRF | Residuals Management | DB | PC-792 | Pending Close-out | 2013-05-23 | 2016-10-31 | 134190.5 | 1691 | 60 | 26 | 0 | 0 | 0 | 0 | 86 | 135967.5 | > 20 | SAWL/SRF | CTA
75 | 1256 | Water Treatment Plant /Pump Station Allowance | 1701 | 170100 | Water | Water | Programs | Programs | D/C | NA | Not Yet Started | NA | NA | 0 | 12645 | 19650 | 20000 | 20000 | 10000 | 10000 | 0 | 79650 | 92295 | > 20 | DE | CTA
184 | 1257 | Wastewater Treatment Plant, Lift Station and Wastewater Collection System Structures Allowance | 2601 | 260100 | Wastewater | Wastewater | Programs | Programs | C | NA | Not Yet Started | NA | NA | 0 | 4555 | 9421 | 10000 | 12500 | 12500 | 10000 | 0 | 54421 | 58976 | > 20 | DE | CTA
238 | 1257 | Wastewater Treatment Plant, Lift Station and Wastewater Collection System Structures Allowance | 2601 | 260100 | Wastewater | Wastewater | Programs | Programs | S/D/CA | NA | Not Yet Started | NA | NA | 0 | 0 | 2000 | 2000 | 2500 | 2500 | 2000 | 0 | 11000 | 11000 | > 20 | DE | CTA
183 | 1257 | Wastewater Treatment Plant, Lift Station and Wastewater Collection System Structures Allowance | 2601 | 260100 | Wastewater | Wastewater | Programs | Programs | C | SCP-PC-014 | Active | TBD | TBD | 0 | 600 | 579 | 0 | 0 | 0 | 0 | 0 | 579 | 1179 | > 20 | DE | CTA
237 | 1257 | Wastewater Treatment Plant, Lift Station and Wastewater Collection System Structures Allowance | 2601 | 260100 | Wastewater | Wastewater | Programs | Programs | C | SCP-PC-016G | Pending Close-out | 2016-04-22 | 2017-04-17 | 0 | 432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 432 | > 20 | DE | CTA
146 | 1263 | Sewer and Interceptor Evaluation and Rehabilitation Program | 2602 | 260200 | Wastewater | Wastewater | Programs | Programs | C | NA | Not Yet Started | NA | NA | 0 | 0 | 5360 | 7360 | 18400 | 18400 | 18400 | 0 | 67920 | 67920 | > 20 | Bond | CTA
149 | 1263 | Sewer and Interceptor Evaluation and Rehabilitation Program | 2602 | 260200 | Wastewater | Wastewater | Programs | Programs | S/D/C | CS-068 | Not Yet Started | NA | NA | 0 | 2464 | 2000 | 0 | 0 | 0 | 0 | 0 | 2000 | 4464 | > 20 | Bond | CTA
147 | 1263 | Sewer and Interceptor Evaluation and Rehabilitation Program | 2602 | 260200 | Wastewater | Wastewater | Programs | Programs | D | NA | Not Yet Started | NA | NA | 0 | 0 | 400 | 400 | 1000 | 1000 | 1000 | 0 | 3800 | 3800 | > 20 | Bond | CTA
148 | 1263 | Sewer and Interceptor Evaluation and Rehabilitation Program | 2602 | 260200 | Wastewater | Wastewater | Programs | Programs | S | NA | Not Yet Started | NA | NA | 0 | 0 | 218 | 240 | 600 | 600 | 600 | 0 | 2258 | 2258 | > 20 | I&E | CTA
239 | 1263 | Sewer and Interceptor Evaluation and Rehabilitation Program | 2602 | 260200 | Wastewater | Wastewater | Programs | Programs | S/D/CA | PO-005030 | Under Procurement | NA | NA | 0 | 148 | 22 | 0 | 0 | 0 | 0 | 0 | 22 | 170 | > 20 | Bond | CTA
20 | 1264 | Water Production Flow Metering Improvements at NE, SW, and SPW WTP | 114 | 114003 | Water | Water | Treatment Plants & Facilities | Springwells | C | NA | Not Yet Started | NA | NA | 0 | 1000 | 8800 | 2100 | 1000 | 0 | 0 | 0 | 11900 | 12900 | < 20 | I&E | CTA
21 | 1265 | Miscellaneous Concrete Improvements at Springwells WTP | 114 | 114004 | Water | Water | Treatment Plants & Facilities | Springwells | C | SP-570 | Active | 2015-11-18 | 2016-10-13 | 397.7223 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 997.7223 | > 20 | Bond | CTA
22 | 1266 | Administration Building Improvements at Springwells WTP | 114 | 114005 | Water | Water | Treatment Plants & Facilities | Springwells | S/D/C | NA | Not Yet Started | NA | NA | 0 | 0 | 0 | 300 | 1700 | 0 | 0 | 0 | 2000 | 2000 | > 20 | DE | CTA
23 | 1267 | Replacement of Rapid Mix Units at Springwells WTP 1958 Process Train | 114 | 114006 | Water | Water | Treatment Plants & Facilities | Springwells | C | NA | Not Yet Started | NA | NA | 0 | 0 | 800 | 197 | 0 | 0 | 0 | 0 | 997 | 997 | > 20 | DE | CTA
207 | 1267 | Replacement of Rapid Mix Units at Springwells WTP 1958 Process Train | 114 | 114006 | Water | Water | Treatment Plants & Facilities | Springwells | D/C | SCP-CS-045 | Active | 2017-02-06 | 2019-05-09 | 0 | 100 | 75 | 78 | 0 | 0 | 0 | 0 | 153 | 253 | > 20 | DE | CTA
24 | 1268 | Powdered Activated Carbon System Improvements at Springwells WTP | 114 | 114007 | Water | Water | Treatment Plants & Facilities | Springwells | S/D/C | NA | Not Yet Started | NA | NA | 0 | 0 | 0 | 0 | 900 | 2000 | 0 | 0 | 2900 | 2900 | > 20 | DE | CTA
25 | 1269 | 1930 Sedimentation Basin Sluice Gates, Guides & Hoists Improvements at Springwells WTP | 114 | 114008 | Water | Water | Treatment Plants & Facilities | Springwells | S/D/C | NA | Not Yet Started | NA | NA | 0 | 0 | 1200 | 2000 | 4000 | 300 | 0 | 0 | 7500 | 7500 | > 20 | DE | CTA
62 | 1270 | Isolation Gate Valves for Line Pumps for West Service Center Pumping Station | 132 | 132003 | Water | Water | SCC | Pump Station/Reservoir | D/C | NA | Not Yet Started | NA | NA | 0 | 0 | 521 | 1000 | 0 | 0 | 0 | 0 | 1521 | 1521 | > 20 | DE | CTA
63 | 1271 | Hydraulic Surge Control for North Service Center Pumping Station | 132 | 132004 | Water | Water | SCC | Pump Station/Reservoir | D/C | NA | Not Yet Started | NA | NA | 0 | 0 | 500 | 2000 | 100 | 0 | 0 | 0 | 2600 | 2600 | > 20 | DE | CTA
64 | 1271 | Hydraulic Surge Control for North Service Center Pumping Station | 132 | 132004 | Water | Water | SCC | Pump Station/Reservoir | S | SCP-CS-054 | Not Yet Started | TBD | TBD | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | > 20 | I&E | CTA
10 | 1272 | Yard Piping Replacement at Northeast Water Treatment Plant | 112 | 112001 | Water | Water | Treatment Plants & Facilities | Northeast | D/C | NA | Not Yet Started | NA | NA | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 800 | 800 | > 20 | DE | CTA
223 | 1273 | Low Lift Pumping Plant Caisson Rehabilitation at Northeast WTP | 112 | 112002 | Water | Water | Treatment Plants & Facilities | Northeast | C | NA | Not Yet Started | NA | NA | 0 | 0 | 1053 | 0 | 0 | 0 | 0 | 0 | 1053 | 1053 | < 20 | DE | CTA
11 | 1273 | Low Lift Pumping Plant Caisson Rehabilitation at Northeast WTP | 112 | 112002 | Water | Water | Treatment Plants & Facilities | Northeast | S/D/CA | CS-1744 | Active | NA | NA | 0 | 150 | 130 | 0 | 0 | 0 | 0 | 0 | 130 | 280 | > 20 | DE | CTA
34 | 1274 | Miscellaneous Concrete and Road Improvements at Waterworks Park WTP | 115 | 115002 | Water | Water | Treatment Plants & Facilities | Water Works Park | C | WW-538 | Not Yet Started | 2016-07-15 | 2017-09-08 | 760.9489 | 2275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3035.9489 | > 20 | Bond | CTA
13 | 1277 | High Lift Pump Discharge Valve Actuators Replacement at Southwest WTP | 113 | 113002 | Water | Water | Treatment Plants & Facilities | Southwest | D/C | NA | Not Yet Started | NA | NA | 0 | 160 | 160 | 900 | 900 | 0 | 0 | 0 | 1960 | 2120 | > 20 | DE | CTA
78 | 1279 | Roofing Systems Replacement at Water Plants and Booster Pump Stations | 331 | 331001 | Water | Centralized Services | Facilities | General Purpose | S/D/C | NA | Not Yet Started | NA | NA | 0 | 3000 | 3000 | 3000 | 2500 | 0 | 0 | 0 | 8500 | 11500 | > 20 | DE | CTA
2 | 1280 | Miscellaneous Mechanical Improvements at Lake Huron WTP | 111 | 111002 | Water | Water | Treatment Plants & Facilities | Lake Huron | C | NA | Not Yet Started | NA | NA | 0 | 0 | 800 | 3000 | 3000 | 400 | 0 | 0 | 7200 | 7200 | > 20 | DE | CTA
3 | 1280 | Miscellaneous Mechanical Improvements at Lake Huron WTP | 111 | 111002 | Water | Water | Treatment Plants & Facilities | Lake Huron | S/D/CA | CS-1732 | Active | TBD | TBD | 0 | 250 | 150 | 130 | 50 | 22 | 0 | 0 | 352 | 602 | > 20 | DE | CTA
203 | 1280 | Miscellaneous Mechanical Improvements at Lake Huron WTP | 111 | 111002 | Water | Water | Treatment Plants & Facilities | Lake Huron | C | NA | Under Procurement | NA | NA | 0 | 20 | 80 | 0 | 0 | 0 | 0 |  | 80 | 100 | > 20 | DE | CTA
14 | 1283 | Replacement of Butterfly Valves and Sluice Gates for Rapid Mix Chamber at Southwest WTP | 113 | 113003 | Water | Water | Treatment Plants & Facilities | Southwest | S/D/C | NA | Not Yet Started | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2940 | 0 | 2940 | > 20 | DE | CTA
125 | 1284 | Complex I Incinerators Decommissioning and Reusability at Wastewater Treatment Plant (WRRF) | 213 | 213005 | Wastewater | Wastewater | WRRF | Residuals Management | S/D/CA/C | NA | Not Yet Started | NA | NA | 0 | 0 | 800 | 200 | 0 | 0 | 0 | 0 | 1000 | 1000 | > 20 | DE | CTA
124 | 1284 | Complex I Incinerators Decommissioning and Reusability at Wastewater Treatment Plant (WRRF) | 213 | 213005 | Wastewater | Wastewater | WRRF | Residuals Management | S/D/CA/C | NA | Not Yet Started | NA | NA | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | > 20 | DE | CTA
130 | 1285 | Construction of new Industrial Waste Control Division and Analytical Laboratory Operations | 214 | 214001 | Wastewater | Wastewater | WRRF | IWC | C | NA | Not Yet Started | NA | NA | 0 | 0 | 5000 | 2000 | 0 | 0 | 0 | 0 | 7000 | 7000 | > 20 | DE | IWC
150 | 1286 | Oakwood District Intercommunity Relief Sewer Modification at Oakwood District | 222 | 222001 | Wastewater | Wastewater | Field Services | Interceptors | C | NA | Not Yet Started | NA | NA | 0 | 0 | 0 | 0 | 2400 | 5300 | 2100 | 0 | 9800 | 9800 | > 20 | Bond | CTA
151 | 1286 | Oakwood District Intercommunity Relief Sewer Modification at Oakwood District | 222 | 222001 | Wastewater | Wastewater | Field Services | Interceptors | S/D/CA | NA | Not Yet Started | NA | NA | 0 | 0 | 0 | 550 | 350 | 200 | 100 | 0 | 1200 | 1200 | > 20 | Bond | CTA
99 | 1287 | Pump Station No. 2 Improvements Phase II at Wastewater Treatment Plant (WRRF) | 211 | 211005 | Wastewater | Wastewater | WRRF | Primary Treatment | S/D/CA | NA | Not Yet Started | NA | NA | 0 | 0 | 600 | 300 | 300 | 200 | 0 | 0 | 1400 | 1400 | > 20 | DE | CTA
98 | 1287 | Pump Station No. 2 Improvements Phase II at Wastewater Treatment Plant (WRRF) | 211 | 211005 | Wastewater | Wastewater | WRRF | Primary Treatment | C | NA | Not Yet Started | NA | NA | 0 | 0 | 0 | 1400 | 4500 | 3500 | 0 | 0 | 9400 | 9400 | > 20 | DE | CTA
65 | 1288 | Energy Management: Evaluate Alternatives and Recommend Corrective Actions to Improve Power Factors (PF) at Various GLWA Booster Pumping Stations | 132 | 132005 | Water | Water | SCC | Pump Station/Reservoir | S | NA | Not Yet Started | NA | NA | 0 | 0 | 125 | 125 | 0 | 0 | 0 | 0 | 250 | 250 | > 20 | I&E | CTA
4 | 1289 | Evaluation of Flocculation Improvement Alternatives at the LHWTP | 111 | 111003 | Water | Water | Treatment Plants & Facilities | Lake Huron | S | NA | Not Yet Started | NA | NA | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | > 20 | I&E | CTA
76 | 1291 | As Needed Construction Materials, Environmental Media and Special Testing Services, Construction Inspection, and Other Technical Services | 1702 | 170200 | Water | Water | Programs | Programs | S/D/CA | CS-1726 | Not Yet Started | TBD | TBD | 0 | 0 | 500 | 500 | 500 | 0 | 0 | 0 | 1500 | 1500 | > 20 | DE | CTA
36 | 1292 | Miscellaneous Improvements to Raw Water Tunnels, Shafts and Related Structures | 116 | 116001 | Water | Water | Treatment Plants & Facilities | General Purpose | D/CA/C | NA | Not Yet Started | TBD | TBD | 0 | 0 | 1000 | 1000 | 500 | 0 | 0 | 0 | 2500 | 2500 | > 20 | DE | CTA
66 | 1293 | Pressure and Control Improvements at the Electric, Ford Road, Michigan, and West Chicago Water Booster Pumping Stations | 132 | 132006 | Water | Water | SCC | Pump Station/Reservoir | S/D/CA | CS-1749 | Under Procurement | TBD | TBD | 0 | 0 | 200 | 250 | 0 | 0 | 0 | 0 | 450 | 450 | < 20 | I&E | CTA
220 | 1293 | Pressure and Control Improvements at the Electric, Ford Road, Michigan, and West Chicago Water Booster Pumping Stations | 132 | 132006 | Water | Water | SCC | Pump Station/Reservoir | C | NA | Not Yet Started | NA | NA | 0 | 0 | 0 | 2550 | 0 | 0 | 0 | 0 | 2550 | 2550 | < 20 | I&E | CTA
67 | 1294 | Energy Management: Freeze Protection Pump Installation at Imlay Pumping Station | 132 | 132007 | Water | Water | SCC | Pump Station/Reservoir | D/C | NA | Not Yet Started | NA | NA | 0 | 0 | 200 | 500 | 300 | 0 | 0 | 0 | 1000 | 1000 | > 20 | DE | CTA
26 | 1295 | Springwells Water Treatment Plant Service Area Redundancy Study | 114 | 114009 | Water | Water | Treatment Plants & Facilities | Springwells | S | CS-1772 | Not Yet Started | TBD | TBD | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | > 20 | I&E | CTA
68 | 1296 | Needs Assessment Study for all Water Booster Pumping Stations | 132 | 132008 | Water | Water | SCC | Pump Station/Reservoir | S | SCP-CS-052 | Not Yet Started | 2016-06-05 | 2017-07-01 | 0 | 500 | 1200 | 0 | 0 | 0 | 0 | 0 | 1200 | 1700 | > 20 | I&E | CTA
15 | 1297 | Residual Handling Facility's Decant Flow Modifications at Southwest WTP | 113 | 113004 | Water | Water | Treatment Plants & Facilities | Southwest | C | NA | Not Yet Started | TBD | TBD | 0 | 0 | 3000 | 2269 | 0 | 0 | 0 | 0 | 5269 | 5269 | > 20 | DE | CTA
16 | 1297 | Residual Handling Facility's Decant Flow Modifications at Southwest WTP | 113 | 113004 | Water | Water | Treatment Plants & Facilities | Southwest | S/D/CA | CS-1730 | Not Yet Started | TBD | TBD | 0 | 100 | 100 | 40 | 0 | 0 | 0 | 0 | 140 | 240 | > 20 | DE | CTA
5 | 1298 | Electrical Tunnel Rehabilitation at Lake Huron WTP | 111 | 111004 | Water | Water | Treatment Plants & Facilities | Lake Huron | C | NA | Not Yet Started | NA | NA | 0 | 0 | 1000 | 3000 | 1600 | 0 | 0 | 0 | 5600 | 5600 | > 20 | DE | CTA
6 | 1299 | Miscellaneous Concrete Improvements at the Lake Huron WTP | 111 | 111005 | Water | Water | Treatment Plants & Facilities | Lake Huron | C | LH-397 | Not Yet Started | 2017-01-08 | 2017-03-09 | 0 | 600 | 323 | 0 | 0 | 0 | 0 | 0 | 323 | 923 | > 20 | DE | CTA
8 | 1300 | Replacement of Filter Instrumentation and Raw Water Flow Metering Improvements at Lake Huron WTP | 111 | 111006 | Water | Water | Treatment Plants & Facilities | Lake Huron | S/D/CA | CS-1771 | Not Yet Started | TBD | TBD | 0 | 100 | 600 | 150 | 150 | 0 | 0 | 0 | 900 | 1000 | > 20 | DE | CTA
7 | 1300 | Replacement of Filter Instrumentation and Raw Water Flow Metering Improvements at Lake Huron WTP | 111 | 111006 | Water | Water | Treatment Plants & Facilities | Lake Huron | C | NA | Not Yet Started | TBD | TBD | 0 | 0 | 0 | 12000 | 11630 | 0 | 0 | 0 | 23630 | 23630 | > 20 | DE | CTA
35 | 1301 | Comprehensive Condition Assessment at Waterworks Park WTP | 115 | 115003 | Water | Water | Treatment Plants & Facilities | Water Works Park | S | NA | Not Yet Started | NA | NA | 0 | 200 | 375 | 0 | 0 | 0 | 0 | 0 | 375 | 575 | > 20 | I&E | CTA
225 | 1302 | Rouge River Outfall (RRO) Disinfection (Alternative) | 212 | 212006 | Wastewater | Wastewater | WRRF | Secondary Treatment & Disinfection | C | PC-797 | Not Yet Started | 2016-02-19 | 2019-12-31 | 0 | 2840 | 15000 | 15000 | 8920 | 0 | 0 | 0 | 38920 | 41760 | > 20 | SRF | CTA
115 | 1302 | Rouge River Outfall (RRO) Disinfection (Alternative) | 212 | 212006 | Wastewater | Wastewater | WRRF | Secondary Treatment & Disinfection | CM | CS-1781 | Under Procurement | TBD | TBD | 0 | 1000 | 800 | 520 | 100 | 0 | 0 | 0 | 1420 | 2420 | > 20 | SRF | CTA
116 | 1302 | Rouge River Outfall (RRO) Disinfection (Alternative) | 212 | 212006 | Wastewater | Wastewater | WRRF | Secondary Treatment & Disinfection | S/D/C | PC-797 | Under Procurement | 2016-02-19 | 2019-12-31 | 728.573 | 2690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3418.573 | > 20 | SRF | CTA
73 | 1303 | Suburban Water Meter Pit Rehabilitation and Meter Replacement | 1709 | 170900 | Water | Water | Programs | Programs | D/C | NA | Not Yet Started | NA | NA | 0 | 500 | 4000 | 4000 | 4000 | 4000 | 4000 | 0 | 20000 | 20500 | > 20 | DE | Suburban Only
217 | 1305 | New Waterworks Park to Northeast Transmission Main | 122 | 122003 | Water | Water | Field Services | Transmission System | S | CS-152 | Under Procurement | NA | NA | 0 | 0 | 1500 | 2000 | 0 | 0 | 0 | 0 | 3500 | 3500 | > 20 | I&E | CTA
216 | 1305 | New Waterworks Park to Northeast Transmission Main | 122 | 122003 | Water | Water | Field Services | Transmission System | C | NA | Not Yet Started | NA | NA | 0 | 0 | 0 | 0 | 0 | 36000 | 36000 | 35650 | 72000 | 107650 | > 20 | Bond | CTA
46 | 1305 | New Waterworks Park to Northeast Transmission Main | 122 | 122003 | Water | Water | Field Services | Transmission System | D/CA | NA | Not Yet Started | NA | NA | 0 | 0 | 0 | 3000 | 10000 | 2000 | 2000 | 1850 | 17000 | 18850 | > 20 | Bond | CTA
27 | 1306 | Yard Piping Improvements at Springwells WTP | 114 | 114010 | Water | Water | Treatment Plants & Facilities | Springwells | S/D/C | NA | Not Yet Started | NA | NA | 0 | 0 | 0 | 2000 | 7000 | 8000 | 8000 | 0 | 25000 | 25000 | > 20 | DE | CTA
28 | 1307 | Steam, Condensate Return, and Compressed Air Piping Improvements at Springwells WTP | 114 | 114011 | Water | Water | Treatment Plants & Facilities | Springwells | C | NA | Not Yet Started | TBD | TBD | 0 | 0 | 3000 | 2250 | 0 | 0 | 0 | 0 | 5250 | 5250 | > 20 | DE | CTA
29 | 1307 | Steam, Condensate Return, and Compressed Air Piping Improvements at Springwells WTP | 114 | 114011 | Water | Water | Treatment Plants & Facilities | Springwells | S/D/CA | CS-1671 | Not Yet Started | TBD | TBD | 0 | 300 | 450 | 250 | 0 | 0 | 0 | 0 | 700 | 1000 | > 20 | DE | CTA
126 | 1309 | Improvements to Sludge Feed Pumps at Dewatering Facilities | 213 | 213006 | Wastewater | Wastewater | WRRF | Residuals Management | S/D/C | NA | Active | NA | NA | 0 | 33 | 402 | 750 | 0 | 0 | 0 | 0 | 1152 | 1185 | > 20 | DE | CTA
127 | 1311 | Modification to Incinerator Sludge Feed Systems at Complex -II | 213 | 213007 | Wastewater | Wastewater | WRRF | Residuals Management | C | NA | Not Yet Started | NA | NA | 0 | 0 | 9100 | 7822 | 0 | 0 | 0 | 0 | 16922 | 16922 | > 20 | DE | CTA
226 | 1311 | Modification to Incinerator Sludge Feed Systems at Complex -II | 213 | 213007 | Wastewater | Wastewater | WRRF | Residuals Management | S/D/CA | CS-060 | Under Procurement | NA | NA | 0 | 1500 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 2000 | > 20 | DE | CTA
100 | 1312 | Rehabilitation of Main Lift Pumps at Pump Station No. 1 | 211 | 211006 | Wastewater | Wastewater | WRRF | Primary Treatment | S/D/C | NA | Not Yet Started | NA | NA | 0 | 0 | 600 | 350 | 125 | 100 | 0 | 0 | 1175 | 1175 | > 20 | DE | CTA
224 | 1312 | Rehabilitation of Main Lift Pumps at Pump Station No. 1 | 211 | 211006 | Wastewater | Wastewater | WRRF | Primary Treatment | C | NA | Not Yet Started | NA | NA | 0 | 0 | 0 | 5000 | 5000 | 1954 | 0 | 0 | 11954 | 11954 | > 20 | DE | CTA
102 | 1314 | Replacement of Bar Racks at Pump Station No.2 | 211 | 211007 | Wastewater | Wastewater | WRRF | Primary Treatment | S/D/CA | NA | Not Yet Started | NA | NA | 0 | 0 | 650 | 400 | 250 | 100 | 0 | 0 | 1400 | 1400 | > 20 | DE | CTA
101 | 1314 | Replacement of Bar Racks at Pump Station No.2 | 211 | 211007 | Wastewater | Wastewater | WRRF | Primary Treatment | C | NA | Not Yet Started | NA | NA | 0 | 0 | 0 | 2500 | 3050 | 2717 | 0 | 0 | 8267 | 8267 | > 20 | DE | CTA
167 | 1315 | Freud & Conner Creek Pump Station Improvements | 232 | 232002 | Wastewater | Wastewater | SCC | Pumping Stations | D | NA | Not Yet Started | NA | NA | 0 | 340 | 3400 | 0 | 0 | 0 | 0 | 0 | 3400 | 3740 | > 20 | DE | CTA
236 | 1315 | Freud & Conner Creek Pump Station Improvements | 232 | 232002 | Wastewater | Wastewater | SCC | Pumping Stations | C | CON-109 | Under Procurement | NA | NA | 0 | 1964 | 2000 | 0 | 0 | 0 | 0 | 0 | 2000 | 3964 | > 20 | DE | CTA
168 | 1315 | Freud & Conner Creek Pump Station Improvements | 232 | 232002 | Wastewater | Wastewater | SCC | Pumping Stations | S | NA | Not Yet Started | NA | NA | 0 | 100 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 600 | > 20 | I&E | CTA
166 | 1315 | Freud & Conner Creek Pump Station Improvements | 232 | 232002 | Wastewater | Wastewater | SCC | Pumping Stations | C | NA | Not Yet Started | NA | NA | 0 | 5636 | 0 | 5100 | 2460 | 1000 | 0 | 0 | 8560 | 14196 | > 20 | DE | CTA
204 | 1318 | Lake Huron WTP-Raw Sludge Clarifier and Raw Sludge Pumping System Improvements | 111 | 111007 | Water | Water | Treatment Plants & Facilities | Lake Huron | S/D/CA | CS-171 | Under Procurement | NA | NA | 0 | 0 | 50 | 920 | 321 | 0 | 0 |  | 1291 | 1291 | > 20 | DE | CTA
9 | 1318 | Lake Huron WTP-Raw Sludge Clarifier and Raw Sludge Pumping System Improvements | 111 | 111007 | Water | Water | Treatment Plants & Facilities | Lake Huron | C | NA | Not Yet Started | NA | NA | 0 | 0 | 0 | 0 | 5842 | 0 | 0 | 0 | 5842 | 5842 | > 20 | DE | CTA
30 | 1320 | Springwells Water Treatment Plant 1930 Filter Building-Roof Replacement | 114 | 114012 | Water | Water | Treatment Plants & Facilities | Springwells | C | NA | Not Yet Started | NA | NA | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | > 20 | DE | CTA
219 | 1321 | 96-inch Main Relocation, Isolation Valves Installations, and New Parallel Main | 122 | 122004 | Water | Water | Field Services | Transmission System | S | CS-165 | Under Procurement | NA | NA | 0 | 500 | 1500 | 0 | 0 | 0 | 0 | 0 | 1500 | 2000 | > 20 | I&E | CTA
47 | 1321 | 96-inch Main Relocation, Isolation Valves Installations, and New Parallel Main | 122 | 122004 | Water | Water | Field Services | Transmission System | C | NA | Not Yet Started | NA | NA | 0 | 0 | 0 | 0 | 30000 | 30000 | 30000 | 30000 | 90000 | 120000 | > 20 | Bond | CTA
218 | 1321 | 96-inch Main Relocation, Isolation Valves Installations, and New Parallel Main | 122 | 122004 | Water | Water | Field Services | Transmission System | D/CA | NA | Not Yet Started | NA | NA | 0 | 0 | 0 | 6000 | 5900 | 1700 | 1700 | 1700 | 15300 | 17000 | > 20 | Bond | CTA
48 | 1323 | Transmission System Water Main Work - Replacement of Schoolcraft Water Main | 122 | 122005 | Water | Water | Field Services | Transmission System | C | NA | Not Yet Started | NA | NA | 0 | 0 | 0 | 7300 | 7250 | 0 | 0 | 0 | 14550 | 14550 | > 20 | Bond | CTA
49 | 1324 | Transmission System Water Main Work-Wick Road Parallel Water Main | 122 | 122006 | Water | Water | Field Services | Transmission System | C | NA | Not Yet Started | NA | NA | 0 | 10000 | 9350 | 0 | 0 | 0 | 0 | 0 | 9350 | 19350 | > 20 | Bond | CTA
222 | 1325 | Reservoir Inspection, Design and Rehabilitation at Imlay Station, Adams Station, Haggerty Station, LH-WTP, SP-WTP and SW-WTP | 1708 | 170800 | Water | Water | Programs | Programs | S/D/CA | CS-151 | Not Yet Started | NA | NA | 0 | 50 | 1800 | 50 | 50 | 50 | 0 | 0 | 1950 | 2000 | > 20 | DE | CTA
69 | 1325 | Reservoir Inspection, Design and Rehabilitation at Imlay Station, Adams Station, Haggerty Station, LH-WTP, SP-WTP and SW-WTP | 1708 | 170800 | Water | Water | Programs | Programs | C | NA | Not Yet Started | NA | NA | 0 | 0 | 1500 | 2500 | 2500 | 2500 | 0 | 0 | 9000 | 9000 | > 20 | DE | CTA
50 | 1326 | Design and Construction of a new Newburgh Road 24" Main along Newburgh Road between Cherry Hill and Glenwood Avenue | 122 | 122007 | Water | Water | Field Services | Transmission System | D/C | NA | Not Yet Started | NA | NA | 0 | 0 | 1800 | 2200 | 0 | 0 | 0 | 0 | 4000 | 4000 | > 20 | Bond | CTA
37 | 1327 | Pennsylvania, Springwells and Northeast Raw Water Supply Tunnel Improvements based on Contract CS-1623 Inspection Results | 116 | 116002 | Water | Water | Treatment Plants & Facilities | General Purpose | DB | DB-150 | Not Yet Started | NA | NA | 0 | 500 | 2000 | 10000 | 15000 | 4900 | 0 | 0 | 31900 | 32400 | > 20 | DE | CTA
152 | 1329 | Detroit River Interceptor (DRI) Evaluation and Rehabilitation | 222 | 222002 | Wastewater | Wastewater | Field Services | Interceptors | C | NA | Not Yet Started | NA | NA | 0 | 0 | 9200 | 4600 | 4600 | 0 | 0 | 0 | 18400 | 18400 | > 20 | SRF | CTA
153 | 1329 | Detroit River Interceptor (DRI) Evaluation and Rehabilitation | 222 | 222002 | Wastewater | Wastewater | Field Services | Interceptors | D | NA | Not Yet Started | NA | NA | 0 | 0 | 500 | 250 | 250 | 0 | 0 | 0 | 1000 | 1000 | > 20 | Bond | CTA
154 | 1329 | Detroit River Interceptor (DRI) Evaluation and Rehabilitation | 222 | 222002 | Wastewater | Wastewater | Field Services | Interceptors | S | NA | Not Yet Started | NA | NA | 0 | 321 | 300 | 150 | 150 | 0 | 0 | 0 | 600 | 921 | > 20 | I&E | CTA
178 | 1330 | Scheduled Replacement Program of Critical Assets | 2603 | 260300 | Wastewater | Wastewater | Programs | Programs | C | NA | Not Yet Started | NA | NA | 0 | 0 | 1721 | 4500 | 4500 | 4500 | 4500 | 0 | 19721 | 19721 | > 20 | DE | CTA
180 | 1330 | Scheduled Replacement Program of Critical Assets | 2603 | 260300 | Wastewater | Wastewater | Programs | Programs | PO | SCP-001 | Not Yet Started | NA | NA | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | > 20 | DE | CTA
240 | 1330 | Scheduled Replacement Program of Critical Assets | 2603 | 260300 | Wastewater | Wastewater | Programs | Programs | C | CON-143 | Under Procurement | NA | NA | 0 | 500 | 1279 | 0 | 0 | 0 | 0 | 0 | 1279 | 1779 | > 20 | DE | CTA
179 | 1330 | Scheduled Replacement Program of Critical Assets | 2603 | 260300 | Wastewater | Wastewater | Programs | Programs | S/D/CA | NA | Not Yet Started | NA | NA | 0 | 0 | 500 | 500 | 500 | 500 | 500 | 0 | 2500 | 2500 | > 20 | DE | CTA
170 | 1331 | Northeast Pumping Station | 232 | 232003 | Wastewater | Wastewater | SCC | Pumping Stations | D | NA | Not Yet Started | NA | NA | 0 | 0 | 1628 | 0 | 0 | 0 | 0 | 0 | 1628 | 1628 | > 20 | Bond | OMID
171 | 1331 | Northeast Pumping Station | 232 | 232003 | Wastewater | Wastewater | SCC | Pumping Stations | S | NA | Not Yet Started | NA | NA | 0 | 0 | 780 | 0 | 0 | 0 | 0 | 0 | 780 | 780 | > 20 | I&E | OMID
169 | 1331 | Northeast Pumping Station | 232 | 232003 | Wastewater | Wastewater | SCC | Pumping Stations | C | NA | Not Yet Started | NA | NA | 0 | 0 | 0 | 10920 | 13000 | 0 | 0 | 0 | 23920 | 23920 | > 20 | Bond | OMID
155 | 1332 | North Interceptor East Arm (NIEA) Evaluation and Rehabilitation | 222 | 222003 | Wastewater | Wastewater | Field Services | Interceptors | C | NA | Not Yet Started | NA | NA | 0 | 0 | 10120 | 11130 | 2760 | 0 | 0 | 0 | 24010 | 24010 | > 20 | Bond | OMID
156 | 1332 | North Interceptor East Arm (NIEA) Evaluation and Rehabilitation | 222 | 222003 | Wastewater | Wastewater | Field Services | Interceptors | D | NA | Not Yet Started | NA | NA | 0 | 0 | 550 | 530 | 150 | 0 | 0 | 0 | 1230 | 1230 | > 20 | Bond | OMID
246 | 1332 | North Interceptor East Arm (NIEA) Evaluation and Rehabilitation | 222 | 222003 | Wastewater | Wastewater | Field Services | Interceptors | S | NA | Not Yet Started | NA | NA | 0 | 0 | 330 | 340 | 90 | 0 | 0 | 0 | 760 | 760 | > 20 | I&E | OMID
70 | 1334 | Study Phase Services for Proposed East Service Center Booster Pumping Station and Reservoir | 132 | 132009 | Water | Water | SCC | Pump Station/Reservoir | S | NA | Not Yet Started | NA | NA | 0 | 400 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 500 | > 20 | I&E | CTA
71 | 1336 | West Service Center/Duval Rd Division Valve Upgrades | 132 | 132010 | Water | Water | SCC | Pump Station/Reservoir | S/D/C | NA | Not Yet Started | NA | NA | 0 | 0 | 4200 | 7600 | 0 | 0 | 0 | 0 | 11800 | 11800 | > 20 | DE | CTA
80 | 1343 | Energy Management: Electric Metering Improvement Program | 3810 | 381000 | Water | Centralized Services | Programs | Programs | S/D/C | NA | Not Yet Started | NA | NA | 0 | 500 | 500 | 500 | 500 | 500 | 500 | 0 | 2500 | 3000 | < 20 | DE | CTA
191 | 1343 | Energy Management: Electric Metering Improvement Program | 3810 | 381000 | Wastewater | Centralized Services | Programs | Programs | S/D/C | NA | Not Yet Started | NA | NA | 0 | 500 | 500 | 500 | 500 | 500 | 500 | 0 | 2500 | 3000 | < 20 | DE | CTA
181 | 1344 | Sewage Meter Design, Installation, Replacement and Rehabilitation Program | 2604 | 260400 | Wastewater | Wastewater | Programs | Programs | S/D/C | NA | Not Yet Started | NA | NA | 0 | 500 | 500 | 500 | 500 | 500 | 500 | 0 | 2500 | 3000 | > 20 | DE | CTA
242 | 1347 | Energy Management: West Service Center (WSC) VFD Installation | 132 | 132011 | Water | Water | SCC | Pump Station/Reservoir | C | NA | Not Yet Started | NA | NA | 0 | 0 | 1484 | 1484 | 0 | 0 | 0 | 0 | 2968 | 2968 | > 20 | DE | CTA
241 | 1347 | Energy Management: West Service Center (WSC) VFD Installation | 132 | 132011 | Water | Water | SCC | Pump Station/Reservoir | D | NA | Not Yet Started | NA | NA | 0 | 0 | 133 | 133 | 0 | 0 | 0 | 0 | 266 | 266 | > 20 | DE | CTA
72 | 1347 | Energy Management: West Service Center (WSC) VFD Installation | 132 | 132011 | Water | Water | SCC | Pump Station/Reservoir | S | NA | Not Yet Started | NA | NA | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 0 | 100 | 100 | > 20 | I&E | CTA
52 | 1350 | Water System Improvements in Joy Road from Southfield Road to Trinity | 122 | 122009 | Water | Water | Field Services | Transmission System | C | WS-691 | Not Yet Started | 2014-08-11 | 2016-08-10 | 8323.2498 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8423.2498 | > 20 | Bond | CTA
53 | 1351 | Water Main Replacement within the City of Detroit - Joy Rd from Greenfield to Schaefer and Davison Ave from Lindwood to Livernois | 122 | 122010 | Water | Water | Field Services | Transmission System | C | WS-693 | Not Yet Started | 2016-09-06 | 2018-11-05 | 0 | 1369.5 | 1106 | 652 | 0 | 0 | 0 | 0 | 1758 | 3127.5 | > 20 | SRF | CTA
215 | 1355 | Genesee and Lapeer County Transmission System Improvements | 116 | 116003 | Water | Water | Treatment Plants & Facilities | General Purpose | D | NA | Not Yet Started | NA | NA | 0 | 0 | 400 | 200 | 200 | 0 | 0 | 0 | 800 | 800 | > 20 | DE | CTA
39 | 1355 | Genesee and Lapeer County Transmission System Improvements | 116 | 116003 | Water | Water | Treatment Plants & Facilities | General Purpose | C | NA | Not Yet Started | NA | NA | 0 | 0 | 0 | 3000 | 3000 | 0 | 0 | 0 | 6000 | 6000 | > 20 | DE | CTA
54 | 1356 | Transmission System Valve Assessment and Rehabilitation/Replacement | 1705 | 170500 | Water | Water | Programs | Programs | DB | NA | New | NA | NA | 0 | 0 | 2930 | 3100 | 3100 | 3100 | 3100 | 0 | 15330 | 15330 | > 20 | DE | CTA
172 | 1357 | Collection System Backwater Gates and Regulator Gates Rehabilitation | 233 | 233001 | Wastewater | Wastewater | SCC | In System Devices | C | NA | New | NA | NA | 0 | 0 | 846 | 3000 | 3000 | 2000 | 0 | 0 | 8846 | 8846 | > 20 | DE | CTA
173 | 1357 | Collection System Backwater Gates and Regulator Gates Rehabilitation | 233 | 233001 | Wastewater | Wastewater | SCC | In System Devices | D | NA | New | NA | NA | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 375 | 375 | > 20 | DE | CTA
174 | 1357 | Collection System Backwater Gates and Regulator Gates Rehabilitation | 233 | 233001 | Wastewater | Wastewater | SCC | In System Devices | S | NA | New | NA | NA | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | > 20 | I&E | CTA
81 | 1366 | Water Facility Lighting Renovations | 351 | 351001 | Water | Centralized Services | Energy Management | General Purpose | C | NA | New | NA | NA | 0 | 0 | 933 | 933 | 933 | 0 | 0 | 0 | 2799 | 2799 | < 20 | I&E | CTA
143 | 1381 | Rehabilitation of the Screened Final Effluent (SFE) Pump Station and Secondary Water System | 216 | 216006 | Wastewater | Wastewater | WRRF | General Purpose | S/D/CA | NA | New | NA | NA | 0 | 0 | 1700 | 2000 | 2000 | 600 | 500 | 280 | 6800 | 7080 | > 20 | Bond | CTA
142 | 1381 | Rehabilitation of the Screened Final Effluent (SFE) Pump Station and Secondary Water System | 216 | 216006 | Wastewater | Wastewater | WRRF | General Purpose | C | NA | New | NA | NA | 0 | 0 | 0 | 0 | 10000 | 15000 | 15779 | 2141 | 40779 | 42920 | > 20 | Bond | CTA
104 | 1382 | Rehabilitation of Ferric Chloride Feed Systems | 211 | 211008 | Wastewater | Wastewater | WRRF | Primary Treatment | S/D/CA | NA | New | NA | NA | 0 | 0 | 400 | 400 | 200 | 0 | 0 | 0 | 1000 | 1000 | > 20 | DE | CTA
103 | 1382 | Rehabilitation of Ferric Chloride Feed Systems | 211 | 211008 | Wastewater | Wastewater | WRRF | Primary Treatment | C | NA | New | NA | NA | 0 | 0 | 0 | 1000 | 5000 | 2000 | 633 | 0 | 8633 | 8633 | > 20 | DE | CTA
129 | 1383 | Rehabilitation of the Ash Handling Systems | 213 | 213008 | Wastewater | Wastewater | WRRF | Residuals Management | S/D/CA | NA | New | NA | NA | 0 | 0 | 530 | 1045 | 225 | 225 | 125 | 0 | 2150 | 2150 | > 20 | DE | CTA
128 | 1383 | Rehabilitation of the Ash Handling Systems | 213 | 213008 | Wastewater | Wastewater | WRRF | Residuals Management | C | NA | New | NA | NA | 0 | 0 | 0 | 0 | 6000 | 5500 | 4666 | 0 | 16166 | 16166 | > 20 | DE | CTA
228 | 1384 | Rehabilitation of Combined Sewer Overflow (CSO) Retention Treatment Basins (RTB) Screening (Replaces CIP1313) | 215 | 215001 | Wastewater | Wastewater | WRRF | CSO RTB & SDF | C | CON-144 | Under Procurement | NA | NA | 0 | 500 | 1137 | 0 | 0 | 0 | 0 | 0 | 1137 | 1637 | > 20 | DE | 83/17
132 | 1384 | Rehabilitation of Combined Sewer Overflow (CSO) Retention Treatment Basins (RTB) Screening (Replaces CIP1313) | 215 | 215001 | Wastewater | Wastewater | WRRF | CSO RTB & SDF | S/D/CA | NA | New | NA | NA | 0 | 2171 | 1000 | 1400 | 1000 | 200 | 100 | 0 | 3700 | 5871 | > 20 | DE | 83/17
232 | 1384 | Rehabilitation of Combined Sewer Overflow (CSO) Retention Treatment Basins (RTB) Screening (Replaces CIP1313) | 215 | 215001 | Wastewater | Wastewater | WRRF | CSO RTB & SDF | D | CS-116 | Under Procurement | NA | NA | 0 | 200 | 110 | 0 | 0 | 0 | 0 | 0 | 110 | 310 | > 20 | DE | 83/17
131 | 1384 | Rehabilitation of Combined Sewer Overflow (CSO) Retention Treatment Basins (RTB) Screening (Replaces CIP1313) | 215 | 215001 | Wastewater | Wastewater | WRRF | CSO RTB & SDF | C | NA | New | NA | NA | 0 | 0 | 0 | 5000 | 8000 | 7000 | 3510 | 0 | 23510 | 23510 | > 20 | DE | 83/17
230 | 1384 | Rehabilitation of Combined Sewer Overflow (CSO) Retention Treatment Basins (RTB) Screening (Replaces CIP1313) | 215 | 215001 | Wastewater | Wastewater | WRRF | CSO RTB & SDF | C | DWS-065 | Under Procurement | NA | NA | 0 | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390 | > 20 | DE | 83/17
231 | 1384 | Rehabilitation of Combined Sewer Overflow (CSO) Retention Treatment Basins (RTB) Screening (Replaces CIP1313) | 215 | 215001 | Wastewater | Wastewater | WRRF | CSO RTB & SDF | D | CS-172 | Under Procurement | NA | NA | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | > 20 | DE | 83/17
229 | 1384 | Rehabilitation of Combined Sewer Overflow (CSO) Retention Treatment Basins (RTB) Screening (Replaces CIP1313) | 215 | 215001 | Wastewater | Wastewater | WRRF | CSO RTB & SDF | C | CON-145 | Under Procurement | NA | NA | 0 | 167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167 | > 20 | DE | 83/17
111 | 1385 | Rehabilitation of the Secondary Clarifiers | 212 | 212007 | Wastewater | Wastewater | WRRF | Secondary Treatment & Disinfection | S/D/CA | NA | New | NA | NA | 0 | 0 | 301 | 576 | 543 | 540 | 540 | 1499 | 2500 | 3999 | > 20 | DE | CTA
110 | 1385 | Rehabilitation of the Secondary Clarifiers | 212 | 212007 | Wastewater | Wastewater | WRRF | Secondary Treatment & Disinfection | C | NA | New | NA | NA | 0 | 0 | 0 | 3000 | 5000 | 5000 | 5000 | 9000 | 18000 | 27000 | > 20 | DE | CTA
106 | 1386 | Rehabilitation of the Circular Primary Clarifier Scum Removal System | 211 | 211009 | Wastewater | Wastewater | WRRF | Primary Treatment | S/D/CA | NA | New | NA | NA | 0 | 0 | 266 | 324 | 370 | 171 | 170 | 179 | 1301 | 1480 | > 20 | DE | CTA
105 | 1386 | Rehabilitation of the Circular Primary Clarifier Scum Removal System | 211 | 211009 | Wastewater | Wastewater | WRRF | Primary Treatment | C | NA | New | NA | NA | 0 | 0 | 0 | 0 | 1500 | 2500 | 2500 | 2500 | 6500 | 9000 | > 20 | DE | CTA
188 | 1387 | Roofing Systems Replacement at GLWA Wastewater Treatment Plant CSO Retention Treatment Basins (RTB) and Screening Disinfection Facilities (SDF) | 331 | 331002 | Wastewater | Centralized Services | Facilities | General Purpose | C | NA | New | NA | NA | 0 | 0 | 2000 | 2000 | 1000 | 1000 | 500 | 2000 | 6500 | 8500 | > 20 | DE | CTA
189 | 1387 | Roofing Systems Replacement at GLWA Wastewater Treatment Plant CSO Retention Treatment Basins (RTB) and Screening Disinfection Facilities (SDF) | 331 | 331002 | Wastewater | Centralized Services | Facilities | General Purpose | S/D/CA | NA | New | NA | NA | 0 | 0 | 200 | 60 | 60 | 50 | 40 | 140 | 410 | 550 | > 20 | DE | CTA
185 | 1388 | Wastewater System Wide Instrumentation & Control Software and Hardware Upgrade | 251 | 251002 | Wastewater | Wastewater | General Purpose | General Purpose | C | NA | New | NA | NA | 0 | 0 | 0 | 0 | 0 | 2800 | 2563 | 0 | 5363 | 5363 | > 20 | DE | CTA
186 | 1388 | Wastewater System Wide Instrumentation & Control Software and Hardware Upgrade | 251 | 251002 | Wastewater | Wastewater | General Purpose | General Purpose | S/D/CA | NA | New | NA | NA | 0 | 0 | 0 | 0 | 0 | 325 | 174 | 0 | 499 | 499 | > 20 | DE | CTA
31 | 1389 | Springwells Reservoir Fill Line Improvements | 114 | 114013 | Water | Water | Treatment Plants & Facilities | Springwells | C | NA | Not Yet Started | NA | NA | 0 | 0 | 3200 | 4000 | 0 | 0 | 0 | 0 | 7200 | 7200 | > 20 | DE | CTA
32 | 1389 | Springwells Reservoir Fill Line Improvements | 114 | 114013 | Water | Water | Treatment Plants & Facilities | Springwells | D/CA | SCP-CS-038 | Under Procurement | TBD | TBD | 0 | 200 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 300 | > 20 | DE | CTA
177 | 1391 | Collection System In System Storage Devices (ISDs) Improvement | 233 | 233002 | Wastewater | Wastewater | SCC | In System Devices | S | NA | New | NA | NA | 0 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 86 | 86 | > 20 | I&E | CTA
175 | 1391 | Collection System In System Storage Devices (ISDs) Improvement | 233 | 233002 | Wastewater | Wastewater | SCC | In System Devices | C | NA | New | NA | NA | 0 | 0 | 0 | 321 | 2000 | 1000 | 0 | 0 | 3321 | 3321 | > 20 | DE | CTA
176 | 1391 | Collection System In System Storage Devices (ISDs) Improvement | 233 | 233002 | Wastewater | Wastewater | SCC | In System Devices | D | NA | New | NA | NA | 0 | 0 | 0 | 143 | 0 | 0 | 0 | 0 | 143 | 143 | > 20 | DE | CTA
159 | 1392 | Collection System Valve Remote Operation Structures Improvements | 222 | 222004 | Wastewater | Wastewater | Field Services | Interceptors | D | NA | New | NA | NA | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | > 20 | DE | CTA
160 | 1392 | Collection System Valve Remote Operation Structures Improvements | 222 | 222004 | Wastewater | Wastewater | Field Services | Interceptors | S | NA | New | NA | NA | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 41 | 41 | > 20 | I&E | CTA
158 | 1392 | Collection System Valve Remote Operation Structures Improvements | 222 | 222004 | Wastewater | Wastewater | Field Services | Interceptors | C | NA | New | NA | NA | 0 | 0 | 0 | 1000 | 1422 | 0 | 0 | 0 | 2422 | 2422 | > 20 | DE | CTA
161 | 1393 | Collection System Access Hatch Improvements | 222 | 222005 | Wastewater | Wastewater | Field Services | Interceptors | C | NA | New | NA | NA | 0 | 0 | 2932 | 2000 | 2001 | 0 | 0 | 0 | 6933 | 6933 | > 20 | DE | CTA
162 | 1393 | Collection System Access Hatch Improvements | 222 | 222005 | Wastewater | Wastewater | Field Services | Interceptors | D | NA | New | NA | NA | 0 | 0 | 198 | 0 | 0 | 0 | 0 | 0 | 198 | 198 | > 20 | DE | CTA
163 | 1393 | Collection System Access Hatch Improvements | 222 | 222005 | Wastewater | Wastewater | Field Services | Interceptors | S | NA | New | NA | NA | 0 | 0 | 66 | 0 | 0 | 0 | 0 | 0 | 66 | 66 | > 20 | I&E | CTA
227 | 1399 | Phosphorous Recovery at WRRF | 213 | 213009 | Wastewater | Wastewater | WRRF | Residuals Management | C | NA | New | NA | NA | 0 | 0 | 0 | 0 | 1000 | 6000 | 6000 | 0 | 13000 | 13000 | > 20 | I&E | CTA
117 | 1399 | Phosphorous Recovery at WRRF | 213 | 213009 | Wastewater | Wastewater | WRRF | Residuals Management | S/D/CA | NA | New | NA | NA | 0 | 0 | 0 | 500 | 1000 | 250 | 250 | 0 | 2000 | 2000 | > 20 | I&E | CTA
244 | 1400 | Water Transmission Main Asset Assessment Program | 1706 | 170600 | Water | Water | Programs | Programs | C | NA | New | NA | NA | 0 | 0 | 2000 | 2000 | 2000 | 2000 | 2000 | 0 | 10000 | 10000 | > 20 | DE | CTA
243 | 1400 | Water Transmission Main Asset Assessment Program | 1706 | 170600 | Water | Water | Programs | Programs | D | NA | New | NA | NA | 0 | 0 | 426 | 0 | 0 | 0 | 0 | 0 | 426 | 426 | > 20 | DE | CTA
55 | 1400 | Water Transmission Main Asset Assessment Program | 1706 | 170600 | Water | Water | Programs | Programs | S | NA | New | NA | NA | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | > 20 | I&E | CTA
40 | 1401 | Water Treatment Plant Automation Program | 1703 | 170300 | Water | Water | Programs | Programs | C | NA | New | NA | NA | 0 | 0 | 1340 | 1340 | 1340 | 1340 | 1340 | 0 | 6700 | 6700 | < 20 | DE | CTA
221 | 1401 | Water Treatment Plant Automation Program | 1703 | 170300 | Water | Water | Programs | Programs | D | NA | New | NA | NA | 0 | 0 | 160 | 160 | 160 | 160 | 160 | 0 | 800 | 800 | < 20 | DE | CTA
144 | 1402 | DTE Primary Electric 3rd Feed Supply to WRRF | 216 | 216007 | Wastewater | Wastewater | WRRF | General Purpose | C | NA | New | NA | NA | 0 | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 6000 | 6000 | > 20 | DE | CTA
145 | 1402 | DTE Primary Electric 3rd Feed Supply to WRRF | 216 | 216007 | Wastewater | Wastewater | WRRF | General Purpose | S/D/CA | NA | New | NA | NA | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 1000 | 1000 | > 20 | DE | CTA
56 | 1403 | Park-Merriman Water Main-Final Phase | 122 | 122011 | Water | Water | Field Services | Transmission System | C | NA | Not Yet Started | NA | NA | 0 | 0 | 1800 | 2200 | 0 | 0 | 0 | 0 | 4000 | 4000 | > 20 | Bond | CTA
57 | 1404 | 36-inch Water Main in Telegraph Road | 122 | 122012 | Water | Water | Field Services | Transmission System | C | WS-684A | Not Yet Started | 2016-04-25 | 2017-06-24 | 0 | 2000 | 5061 | 0 | 0 | 0 | 0 | 0 | 5061 | 7061 | > 20 | Bond | CTA
58 | 1405 | Lyon Township Transmission Main Extension Project | 122 | 122013 | Water | Water | Field Services | Transmission System | S/D/C | NA | New | NA | NA | 0 | 1300 | 10500 | 12000 | 6000 | 0 | 0 | 0 | 28500 | 29800 | > 20 | Bond | CTA
210 | 1407 | Springwells WTP Underground Fire Protection Loop Improvements | 114 | 114014 | Water | Water | Treatment Plants & Facilities | Springwells | D | NA | New | NA | NA | 0 | 0 | 380 | 0 | 0 | 0 | 0 | 0 | 380 | 380 | > 20 | I&E | CTA
208 | 1407 | Springwells WTP Underground Fire Protection Loop Improvements | 114 | 114014 | Water | Water | Treatment Plants & Facilities | Springwells | C | NA | New | NA | NA | 0 | 0 | 0 | 2529 | 0 | 0 | 0 | 0 | 2529 | 2529 | > 20 | Bond | CTA
209 | 1407 | Springwells WTP Underground Fire Protection Loop Improvements | 114 | 114014 | Water | Water | Treatment Plants & Facilities | Springwells | CA | NA | New | NA | NA | 0 | 0 | 0 | 380 | 0 | 0 | 0 | 0 | 380 | 380 | > 20 | Bond | CTA
233 | 1409 | CSO Outfall Rehabilitation | 222 | 222006 | Wastewater | Wastewater | Field Services | Interceptors | C | NA | New | NA | NA | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 30000 | 36000 | > 20 | DE | CTA
213 | 1410 | Water Works Park WTP Chlorine System Upgrade | 115 | 115004 | Water | Water | Treatment Plants & Facilities | Water Works Park | C | NA | New | NA | NA | 0 | 0 | 500 | 8500 | 0 | 0 | 0 | 0 | 9000 | 9000 | > 20 | Bond | CTA
214 | 1410 | Water Works Park WTP Chlorine System Upgrade | 115 | 115004 | Water | Water | Treatment Plants & Facilities | Water Works Park | D | CS-1721 | New | 2016-07-08 | 2018-01-25 | 0 | 290 | 200 | 200 | 0 | 0 | 0 | 0 | 400 | 690 | > 20 | Bond | CTA
234 | 1411 | NIEA Evaluation and Rehabilitation from WRRF to Gratiot Ave. and Sylvester St. | 222 | 222007 | Wastewater | Wastewater | Field Services | Interceptors | C | NA | New | NA | NA | 0 | 0 | 6300 | 6300 | 6300 | 0 | 0 | 0 | 18900 | 18900 | > 20 | Bond | CTA
235 | 1411 | NIEA Evaluation and Rehabilitation from WRRF to Gratiot Ave. and Sylvester St. | 222 | 222007 | Wastewater | Wastewater | Field Services | Interceptors | D | NA | New | NA | NA | 0 | 0 | 700 | 700 | 700 | 0 | 0 | 0 | 2100 | 2100 | > 20 | Bond | CTA
211 | 1412 | Emergency Grating Replacement at Springwells WTP | 114 | 114015 | Water | Water | Treatment Plants & Facilities | Springwells | C | NA | New | NA | NA | 0 | 250 | 1750 | 0 | 0 | 0 | 0 | 0 | 1750 | 2000 | > 20 | Bond | CTA
212 | 1412 | Emergency Grating Replacement at Springwells WTP | 114 | 114015 | Water | Water | Treatment Plants & Facilities | Springwells | D | NA | New | NA | NA | 0 | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 500 | > 20 | Bond | CTA
44 | 1230b | 48-Inch Water Main Installation at Vining and Wick Roads in Romulus | 122 | 122014 | Water | Water | Field Services | Transmission System | C | MOU-4848 | Active | 2016-03-07 | TBD | 1020.801 | 3514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4534.801 | > 20 | Bond | CTA
45 | 1230c | 30-Inch Water main | 122 | 122015 | Water | Water | Field Services | Transmission System | C | CON-105 | New | NA | NA | 0 | 2327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2327 | > 20 | Bond | CTA
[14 empty] | 469413.2998 | 139469.4061 | 298401 | 391582.33 | 387053 | 256747 | 219550 | 122379 | 1553333.33 | 2284595.0359
Formulas:
Start Date = PhasesTable[[#This Row],[End Date]]-360