## Slide 1
09/17/25
Freud Sanitary Pump Station

## Slide 2: Agenda
System Background
Freud Improvements
  Why is GLWA proposing a Sanitary Pump Station?
  Why was the location chosen?
  Why will Freud St be rerouted?
Design Review
  Design Alternatives
  Exterior Design
Project Progress
  Where are we at?
  What’s next?
Conner Creek Improvements
  System Background
  Storm Station Improvements
  Why is GLWA proposing a new Sanitary Pump Station?
  Where will the new Sanitary Pump Station be located?
  What’s next?
Questions

## Slide 3: System Background

## Slide 4: System Background
Notes: Conner Creek Pump Station – 1929
Storm - 8 Pumps - Total 2,584 MGD
Sanitary - 4 Pumps - Total 215 MGD
Freud Pump Station – 1955
Storm – 8 Pumps – Total 2,325 MGD
Dewatering – 2 Pumps – Total 36 MGD

## Slide 5: Freud Improvements

## Slide 6
Improve the Reliability of Freud Storm Pump Station
  Cleaning
  Inspection
  Maintenance
  Rehabilitation
Maximize GLWA’s ability to keep sewer water levels low during rain events
Help prevent basement backups
Why is GLWA Proposing a Sanitary Pump Station?
Notes: The new Sanitary Station will allow for the isolation of the existing Storm Station to allow for cleaning, inspection, and maintenance that isn’t currently feasible.
- Safety standards are much different than in 1955.
- Bypass pumping would be continuously invasive and disruptive to the neighborhood.
Keeping the existing Storm Station in top running condition allows GLWA to better manage the sewer water levels and respond to rain events.

## Slide 7: Why is GLWA Proposing a Sanitary Pump Station?
Freud Storm Pump Station
Freud Sanitary Pump Station
Fox Creek Relief Sewer
Ashland Relief Sewer
To DRI
Notes: Wet Weather Flow will pass through the station.
Dry Weather Flow will enter the station and be pumped to the DRI.

## Slide 8: Why Was The Location Chosen?
Notes: There is a small window between Tennessee & Algonquin where the Ashland & Fox Creek Relief Sewers run in parallel and allow for the construction of one station instead of 2 separate stations.
Construction of the Sanitary Station in between Conner & Navahoe means that no residents need to be displaced.

## Slide 9: Why Will Freud St Be Rerouted?
Notes: Freud St will need to be rerouted as both the Ashland & Fox Creek Relief Sewer are located directly below Freud St and the Sanitary Station needs to be located directly above both sewers.
Freud will be rerouted around the new Sanitary Station instead of creating a dead end.
Additional questions may revolve around road closures.
- Freud, Conner, & Navahoe are currently scheduled to be closed for the full duration of the project (i.e. 4 years).
- We’re currently working with Kokosing to reduce the Freud closer to a shorter duration (i.e. 2 years).
- Kokosing is planning to install a walking path to maintain safe foot traffic between the south side of Freud, Conner, & Navahoe.

## Slide 10: Design Review

## Slide 11: Design Alternative #1
DWSD – Detroit Water and Sewerage Department
Notes: Install Isolation Structures on the existing station property.
Doesn’t allow for handling of dry weather flows when station is isolated.

## Slide 12: Design Alternative #2
DWSD – Detroit Water and Sewerage Department
Notes: Install Isolation Structures on the existing station property & a Sanitary Station immediately adjacent to the property.
Would result in Freud St being closed permanently between Clairpointe & Tennessee.

## Slide 13: Design Alternative #3
DWSD – Detroit Water and Sewerage Department
Notes: Install a Junction Shaft for the Ashland & Fox Creek Relief Sewers that would combine the two into a single large diameter tunnel feeding a new combined Conner Creek & Freud Pump Station w/new Discharge Channel.
Option was found to be excessively costly >$1B.

## Slide 14: Why was a Variation of Alternative 2 Selected?

## Slide 15
Exterior Design – Conner Street View

## Slide 16
Exterior Design – Freud Street View

## Slide 17
Exterior Design – North Elevation

## Slide 18
Exterior Design – East Elevation

## Slide 19
Exterior Design – South Elevation

## Slide 20
Exterior Design – West Elevation

## Slide 21: Project Progress

## Slide 22
Utility Relocations Complete
DRI Structure Installation
  Traffic Shift
  May-December
36” Force Main Installation
  Navahoe St
  August-December
Rezoning
Where are we at? – Construction
Notes: Utility Relocation
Gas – Complete in February
Electric – Complete in March
Communication (6) – Complete in March
Rezoning
11/21/24 – CPC Public Hearing
01/16/25 – CPC Public Hearing
06/05/25 – CPC Meeting
Additional CPC Meetings?/City Council Meeting?
Bypass Pumping system in place for Sewers during relocation.
Water supplied by Essex Line during relocation.
Utility Relocation - New utilities in place before removal of existing utilities.
Sewer – February
Water - March
Communication – February/March
Freud Street Closure
Dependent on Traffic Study\MOT Approval – January
GLWA to send out notice & social media at least one week ahead of time.
Freud Sanitary Station
Site Setup
Force Main – March
Locate 16’ Sewers - April
Freud Storm Station
Construction activities mostly internal ongoing.

## Slide 23
Rezoning
  City Planning Commission
  Planning & Economic Development Committee
  City Council
Secant Pile Installation
Shaft Excavation
What’s next? – Construction

## Slide 24
What’s next? – Quarterly Meetings

## Slide 25
Website - www.glwater.org/freud-sanitary-pump-station
QR Code -
Email - freudsanitarypumpstation@glwater.org
Phone
  GLWA - (313) 822-7007
  Kokosing - (313) 960-7687
Mailers
Social Media
What’s next? – Communication
Notes: Website
FAQ’s, Map, Meeting Schedule, Presentations, & Contact Info
Email & Phone
Messages returned in a timely manner
Mailers
Yearly – Schedule of Community Update Meetings
Traffic Impacts\Abnormal Project Activities – Minimum of one week
Social Media
Traffic Impact– Minimum of one week

## Slide 26: Conner Creek Improvements

## Slide 27: System Background

## Slide 28
Isolation Gate Installation
  East Jefferson Relief Sewer
  West Jefferson Relief Sewer
Storm Pump Replacements
Improvements to the Storm Station
New Isolation Gates

## Slide 29
Improve Reliability
  Cleaning
  Inspection
  Maintenance
Existing Limitations
160 MGD Firm Capacity
    53 MGD Average Flow
    148 MGD Peak Flow
N+2 Configuration
Why is GLWA proposing a new Sanitary Pump Station?
Notes: Existing Station Limitations
4 Pumps - 145 MGD Firm/215 MGD Total Capacity
Small Wet Well
Pump Isolation/Maintenance Issues

## Slide 30
Where will the new Sanitary Pump Station be located?
Notes: Existing Station Limitations
4 Pumps - 145 MGD Firm/215 MGD Total Capacity
Small Wet Well
Pump Isolation/Maintenance Issues

## Slide 31
Where will the new Sanitary Pump Station be located?
Notes: Existing Station Limitations
4 Pumps - 145 MGD Firm/215 MGD Total Capacity
Small Wet Well
Pump Isolation/Maintenance Issues

## Slide 32
Quarterly Meetings
Additional Meetings
  District 4
    Councilmember Johnson
    Community Advisory Council
    Department of Neighborhoods
Preliminary Plan Review
Exterior Design
What’s next?
Notes: 07/31/25 - Preliminary Plan Review Meeting
2026-2029 – Construction
03/18/25 – 90% Design Workshop
12/11/24 – Quarterly Community Engagement Event
12/05/24 – Introductory Meeting
10/02/24 – 60% Design Workshop

## Slide 33: Questions

## Slide 34: Jefferson Chalmers Topography Relative to Detroit River Levels
5 to 7 ft below Max River Level of 578

## Slide 35: Jefferson Chalmers Topography Relative to Detroit River Levels
2019 & 2020 River Levels reached 577.50
GLWA system protected Jefferson Chalmers Community by removing over 1 Billion Gallons of water from River Inflow
The Freud Pumpstation operated 50% more in run hours in 2019/2020 compared to the average of 2017-2024

## Slide 36: East Side System FIRMs
Flood Plain Designation Jefferson Chalmers in 2021
FEMA : Federal Emergency Management Agency
FIRMs: Flood Insurance Rate Maps
FEMA Flood Map Service Center | Search By Address
Special Flood Hazard Areas
Area with reduced
flood risk due to levees
Notes: Flood plain designation is related surface water flooding and coastal flooding not pluvial flooding. Using the map as an example for the 2021 rain event both locations on the map were significantly overwhelmed by the rain precipitation however, the designation for gross point remains protected based on Levee. In May of 2022 CITY of Detroit in partnership with US Army Corp attempted to present alternatives to achieve similar designation as Gross Point Park shown on the image however the alternativities were not successful.
Both communities experienced similar flooding and precipitation from the 2021.
Here are screenshots from the 2012 FEMA maps (the previous version before 2021). As I mentioned the remapping process for Wayne County started maybe around 2014 or 2015 and the new maps came out in 2021. The remapping had absolutely nothing to do with the high lake levels in 2019-2022. It also has nothing to do with stormwater. The FEMA maps do not consider stormwater flooding at all.

## Slide 37: Dry Weather Flow
Notes: E. Jefferson Relief Sewer receives dry weather flow from Jefferson Chalmers and conveys it to Conner PS
Dry weather flow is pumped to the DRI via Conner PS

## Slide 38: Dry Weather Flow
Jefferson Chalmers Sewer Connection
Notes: Dry Weather Flow
Daily Average – 2.5 MGD
Annual – 910 MG

## Slide 39: Wet Weather Flow
Notes: E. Jefferson Relief and Ashland Relief Sewers receive combined (dry and storm) flows from Jefferson Chalmers
Combined flow is delivered to DRI and Conner RTB via Conner and Freud PSs

## Slide 40: Wet Weather Flow
Jefferson Chalmers Sewer Connection
Flow Divert to Freud @ 545 elev. (65.7 ft Detroit Datum)
Recent Strom Water Reached 554 elev. (74.7 Detroit Datum)
Notes: Wet Weather Flow
Daily Average – N/A MGD
Annual – ~400 MG (rain dependent)
River Inflow (2019/2020)
Daily Average (72 Days) – 13 MGD
Total (72 Days) – 930 MG

## Slide 41: No Station Option – Overhead View

## Slide 42: No Station Option - Heavy Equipment

## Slide 43: No Station Option - Bypass Piping

## Slide 44: No Station Option - Wastewater Pumps

## Slide 45: No Station Option - Generator Power

## Slide 46
Utility Relocation
  Gas
  Electric
  Communication
Rezoning
Freud Street Closure
  Detour
  Fencing
  Path
Where are we at?
Notes: Utility Relocation
Gas – Complete in February
Electric – Complete in March
Communication (6) – Complete in March
Rezoning
11/21/24 – CPC Public Hearing
01/16/25 – CPC Public Hearing
04/17/25 – CPC Meeting
Additional CPC Meetings?/City Council Meeting?
Freud Street Closure
Working with consultants on enhancing road closure signage to limit neighborhood traffic.
New sidewalk around the construction area will be installed before the EOM.
Traffic Study results have determined the Freud St reroute should be Freud to Clairpointe/Conner to Jefferson to Dickerson and back to Freud.
Utility Relocation
DTE-Gas – 01/31/25
DTE-Electric – 02/10/25
Rezoning is in front of CPC. Attend 11/21/24 and going to January meeting
City Council approved the Vacation & Dedication of Freud St on 07/02/24.
EGLE has approved SRF Funding.
Kokosing was issued Contract# 2204605 with an NTP of 07/15/24 and Final Completion Date of 11/12/28.

## Slide 47
Exterior Design – Scale

## Slide 48
Exterior Design – Conner Street View

## Slide 49
Exterior Design – Freud Street View

## Slide 50
Exterior Design – Navahoe & Freud View

## Slide 51: Dry Weather Flow

## Slide 52: Wet Weather Flow

## Slide 53: Temporary Access – Conner Street View

## Slide 54
Exterior Design – Elevations

## Slide 55: System Background
Notes: Conner Creek Pump Station – 1929
Storm - 8 Pumps - Total 2,584 MGD
Sanitary - 4 Pumps - Total 215 MGD
Freud Pump Station – 1955
Storm – 8 Pumps – Total 2,325 MGD
Dewatering – 2 Pumps – Total 36 MGD
Freud Sanitary Station
- Allow for the isolation of the existing Storm Station for cleaning, inspection, and maintenance that isn’t currently feasible.
- Safety standards are much different than in 1955.
- Bypass pumping would be continuously invasive and disruptive to the neighborhood.
Keeping the existing Storm Station in top running condition allows GLWA to better manage the sewer water levels and respond to rain events.

## Slide 56: Project Background
Resiliency
  Power Monitoring and Reliability
  System Access for Routine Maintenance
  Mechanical Upgrades

## Slide 57: Why is the building this size?
Contain Operations
  Crane
  Noise
  Odor
Notes: The building is large enough to fully contain the operations that occur within it.
- Crane for pumps & stop logs.
- Contain noise
- Contain odors